## Sheet1
title | Field2 | Field3 | Field4 | Field5 | Field6 | Field7
PMP Question 101 | Which process of integrative project management documents the actions necessary to define, prepare, integrate, and coordinate all subsidiary plans into a project management plan? | A. Direct and Manage Project WorkB. Monitor and Control Project WorkC. Develop Project CharterD. Develop Project Management Plan | Show Answer | D. Develop Project Management Plan
PMP Question 102 | You are looking at various process improvement models. Which of the following is not a process improvement model? | A. Malcolm-BaldrigeB. Organizational Project Management Maturity Model (OPM3)®C. Capability Maturity Model Integrated (CMMI®)D. Shewhart-Deming | Show Answer | D. Shewhart-Deming | Tagged with Capability Maturity Model Integrated (CMMI) Organizational Project Management Maturity Model (OPM3) process improvement model Shewhart-Deming | Tagged with Capability Maturity Model Integrated (CMMI) Organizational Project Management Maturity Model (OPM3) process improvement model Shewhart-Deming
PMP Question 103 | You are a consulting project manager and have been contracted by an investment bank to run a large information technology project that is expected to last 15 months. During the Direct and Manage Project Work process, you discover that several regulatory requirements have not been addressed in the project management plan. Failure to meet these requirements could result in legal action against the company. However, implementing the technology to comply with these regulations exceeds the budget and scope of the project, and could result in the cancellation of the project. What should you do? | A. Submit a change request to incorporate the missed requirements to the project’s scope.B. Do not do anything as these requirements are not a part of the scope baseline.C. Request additional funds to implement these requirements.D. This is a classical example of scope creep and such requirements must be ignored. | Show Answer | A. Submit a change request to incorporate the missed requirements to the project’s scope. | Tagged with change request | Tagged with change request
PMP Question 104 | The Earned Value Management methodology can be used as a means to: | A. Forecast future performance based on past performanceB. Calculate the number of days left in the projectC. Calculate the value provided to the customerD. Calculate the profitability of the project | Show Answer | A. Forecast future performance based on past performance | Tagged with Earned Value Management methodology | Tagged with Earned Value Management methodology
PMP Question 105 | What similarity exists between a cost-reimbursable contract and a time and material contract? | A. They are open endedB. The closure date is part of the contract.C. They have fixed bonus rates.D. They can never grow in value. | Show Answer | A. They are open ended | Tagged with cost-reimbursable contract | Tagged with cost-reimbursable contract
PMP Question 106 | You are a certified PMP, and have been contact by PMI as part of an investigation they are conducting into allegations of improper conduct by your manager, also a PMP. A complaint has been filed stating that your manager has received bribes related to a large procurement contract on another project. PMI has asked if you would be able to provide information regarding this situation. What should you do? | A. Confront your manager.B. Send PMI project documentation and emails related to the allegations to assist with their investigation.C. Notify the appropriate management immediately.D. Do nothing, citing a conflict of interest. | Show Answer | C. Notify the appropriate management immediately.
PMP Question 107 | You are the project manager for a Fortune 100 IT company and you are currently engaged in an important project. You want to choose the best contractor for a specialized task. What should you do to evaluate potential contractors? | A. Create a lessons learned documentB. Conduct a performance reviewC. Evaluate proposalsD. Perform a Make-or-Buy analysis | Show Answer | C. Evaluate proposals
PMP Question 108 | While rating a proposal, one of the requirements was “The proposed project manager needs to be a certified Project Management Professional, PMP® ” This is an example of: | A. ConstraintsB. Source Selection CriteriaC. AssumptionsD. Good practice | Show Answer | B. Source Selection Criteria | Tagged with Assumptions Constraints Source Selection Criteria | Tagged with Assumptions Constraints Source Selection Criteria
PMP Question 109 | There are several communication methods used to share and distribute information to stakeholders, team members and management. Which of the following communication methods are used during execution phase to notify the public about environmental changes your project is going to cause after implementation? | A. Pull communicationB. Interactive communicationC. Informal communicationD. Push communication | Show Answer | A. Pull communication | Tagged with Informal communication | Tagged with Informal communication
PMP Question 110 | Peter’s project is in execution. The cost management plan and the project budget were approved by all key stakeholders during the planning phase of the project. Recently, the finance manager of the company has notified Peter that his project funding might suffer as another higher priority project has been initiated by the company. Peter is surprised as his project was also a high priority project for the company. What should Peter immediately do? | A. Immediately terminate the project in the best interest of the organizationB. Put the project work on hold until the funds become availableC. Negotiate for funds with the finance manager and the project sponsorD. Release the project team members | Show Answer | C. Negotiate for funds with the finance manager and the project sponsor | Tagged with project sponsor | Tagged with project sponsor
PMP Question 111 | Your company took over the management of a project from another company that went out of business. To minimize disruptions related to the transition, your company hired a number of the employees from the other company. One of these employees has delivered a 300 page document a week ahead of schedule. However, while walking past his desk you notice he has a document opened on his computer with the logo of his former employer. You suspect that some of his work may have been taken from documentation that is the property of the other company. What do you do? | A. Report this to your project stakeholders immediately.B. Determine if any materials belonging to the other company have been copied.C. The copyright material is owned by the client, for whom you are working so this is not a copyright issue.D. Do nothing. Because the company is now out of business, out no one now owns the copyright on that material. | Show Answer | B. Determine if any materials belonging to the other company have been copied. | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 112 | Emily is the project documents controller for a multi-million dollar telecom network deployment project. Emily has just received a document from the project manager. This document contains the project stakeholders’ communication requirements for the current project phase. Emily should update which of the following project documents with this information? | A. Work breakdown structureB. Stakeholders engagement assessment matrixC. Stakeholder management planD. Stakeholder register | Show Answer | C. Stakeholder management plan | Tagged with Stakeholder register Stakeholders engagement Stakeholders engagement assessment matrix | Tagged with Stakeholder register Stakeholders engagement Stakeholders engagement assessment matrix
PMP Question 113 | Which of the following is an output of the Conduct Procurements process? | A. AdvertisingB. Selected SellersC. Independent EstimatesD. Expert Judgment | Show Answer | B. Selected Sellers | Tagged with Advertising Expert judgment Independent Estimates Selected Sellers | Tagged with Advertising Expert judgment Independent Estimates Selected Sellers
PMP Question 114 | You have been managing a research project that is intended to create Genetically Modified fruits using Genetic Engineering techniques. Since many legal issues are involved in this process, you created contingency allowances by using different quantitative analysis methods to account for cost uncertainty. You have just wrapped-up a brainstorming session with your team in the execution phase to monitor new risks evolved in the project over past few weeks and to establish new risk response plans. What should you do if you want to allocate more contingency reserves to account for new risks? | A. Perform the reserve analysis to compare the amount of contingency reserves remaining to the amount of risk remainingB. Perform Monte Carlo analysis to compare the amount of contingency reserves remaining to the amount of risk remainingC. Perform the variance and trend analysis to compare planned results to the actual resultsD. Perform the quantitative risk analysis to determine the outstanding risks | Show Answer | A. Perform the reserve analysis to compare the amount of contingency reserves remaining to the amount of risk remaining | Tagged with contingency reserves reserve analysis | Tagged with contingency reserves reserve analysis
PMP Question 115 | Late in the project cycle, it was discovered that some of the project human resources needed to have been trained on a specific methodology. Ideally, where should these training needs have first been documented? | A. Staffing management planB. In the procurement contractC. In the project scope statementD. In the company HR policy | Show Answer | A. Staffing management plan | Tagged with company HR policy Staffing Management Plan | Tagged with company HR policy Staffing Management Plan
PMP Question 116 | A project is contracted as a Cost-Plus-Incentive-Fee (CPIF) type of contract. The project is negotiated such that if the final costs are less than expected costs, the sharing formula for cost savings is 75:25. The targeted cost is US$ 100,000 with an 8% incentive fee on the targeted cost. If the project comes in at US$ 80,000, what would be the cost of the total contract? | A. US$ 108,000B. US$ 93,000C. US$ 112,000D. US$ 91,400 | Show Answer | B. US$ 93,000 | Tagged with Cost-Plus-Incentive-Fee (CPIF) | Tagged with Cost-Plus-Incentive-Fee (CPIF)
PMP Question 117 | You are planning a storage device migration in a data center. During this phase of the project, who should be controlling the project? | A. Project ManagerB. SME’sC. SponsorD. Management | Show Answer | A. Project Manager
PMP Question 118 | A project needed to monitor the technical performance of the project and capture data related to how many errors or defects had been identified, and how many remained uncorrected. Which of the following techniques should the project use? | A. Scatter diagramB. FlowchartC. HistogramD. Control chart | Show Answer | C. Histogram | Tagged with Flowchart Histogram Scatter diagram | Tagged with Flowchart Histogram Scatter diagram
PMP Question 119 | Factors that influence conflict resolution methods include EXCEPT: | A. Position taken by persons involved.B. Relative importance and intensity of the conflict.C. Political influence of the persons involved.D. Time pressure for resolving the conflict. | Show Answer | C. Political influence of the persons involved.
PMP Question 120 | A project manager is confused about the perspective of the buyer-seller relationship in the context of project procurement management. How would your clarify this? | A. The buyer-seller relationship exists only between organizations external to the acquiring organization.B. The buyer-seller relationship exists only between organizations internal to the acquiring organization.C. The buyer-seller relationship is applicable only when a performing organization is involved.D. The buyer-seller relationship can exist at many levels on one project, and between organizations internal to and external to the acquiring organization. | Show Answer | D. The buyer-seller relationship can exist at many levels on one project, and between organizations internal to and external to the acquiring organization.
PMP Question 121 | The Code of Ethics and Professional Conduct has as its foundation four values identified by practitioners from the global project management community. They are: | A. Respect, fairness, transparency and freedom.B. Responsibility, transparency, fairness and honesty.C. Respect, freedom, honesty and transparency.D. Responsibility, respect, fairness and honesty | Show Answer | D. Responsibility, respect, fairness and honesty | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 122 | Which of the following is incorrect regarding a bidders conference? | A. Questions from each seller should be handled confidentially and not shared with other sellers.B. No bidders should receive preferential treatment, even if they are part of the company’s existing list of approved suppliers.C. Bidders conferences should not involve individual face-to-face meetingsD. All prospective sellers should be allowed to have a common understanding of the procurement. | Show Answer | A. Questions from each seller should be handled confidentially and not shared with other sellers. | Tagged with bidders conference | Tagged with bidders conference
PMP Question 123 | You are fairly new to project management, but have been successfully managing a small project and now management has given you another project to manage, which you are excited about. However, the new project is growing exponentially everyday, you have also learned a project manager you work with managed a similar project last year. What should you do? | A. Wait to see if the scope of the project continues to growB. Get the project assigned to the PM who managed the similar projectC. Obtain Historical Records and get guidance from the project managerD. Speak to the other project manager to develop your project plans | Show Answer | C. Obtain Historical Records and get guidance from the project manager | Tagged with Historical Records | Tagged with Historical Records
PMP Question 124 ( PMBOK 6th edition ) | You are working with your team and are looking at the cost risks in the project. You are your team are currently creating a tornado diagram for the project risks. This is done as a part of which of the following processes? | A. Qualitative Risk AnalysisB. Risk Response PlanningC. Quantitative Risk AnalysisD. Monitor Risks | Show Answer | C. Quantitative Risk Analysis | Tagged with Control Risks Monitor Risks Risk Response Planning tornado diagram | Tagged with Control Risks Monitor Risks Risk Response Planning tornado diagram
PMP Question 125 | The document that formally authorizes a project is the: | A. Project SOWB. Project PlanC. Project CharterD. Project Scope Statement | Show Answer | C. Project Charter
PMP Question 126 | During a presentation to management, you want to display the project schedule with only the key deliverables displayed. What is the correct tool for this purpose? | A. Project schedule network diagramB. Critical path networkC. Milestone chartD. Critical chain diagram | Show Answer | C. Milestone chart | Tagged with Critical chain diagram Critical path network milestone chart Project schedule network diagram | Tagged with Critical chain diagram Critical path network milestone chart Project schedule network diagram
PMP Question 127 ( PMBOK 6th edition ) | The Risk Register contains details of all identified risks and current status. It is a document containing the results of: | A. Plan Risk ResponsesB. Identify RisksC. Monitor RisksD. Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis and Plan Risk Responses | Show Answer | D. Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis and Plan Risk Responses | Tagged with Control Risks Monitor Risks Risk Register | Tagged with Control Risks Monitor Risks Risk Register
PMP Question 128 | The Identify Stakeholders process has four inputs. Three of them are project charter, enterprise environmental factors and organizational process assets. What is the fourth one? | A. Procurement documentsB. Stakeholder registerC. Stakeholder engagement matrixD. Stakeholder management plan | Show Answer | A. Procurement documents
PMP Question 129 | Which of the following may not be considered an attribute of a project? | A. Repetitive elements may be present in some project deliverables.B. The impact of a project usually ends when the project ends.C. A project can involve a single person.D. There is uncertainty about the product that the project creates. | Show Answer | B. The impact of a project usually ends when the project ends.
PMP Question 130 | Which of the following models describes stakeholders based on their power, urgency and legitimacy? | A. Influence / Impact gridB. Power / influence gridC. Power / Interest gridD. Salience model | Show Answer | D. Salience model | Tagged with Salience model | Tagged with Salience model
PMP Question 131 | A project manager is determining dependencies that will require a lead or a lag to accurately define the logical relationship. Which of the following correctly describes leads or lags? | A. A lead allows a successor activity to be delayed.B. A lag directs a delay in the predecessor activity.C. A lag allows an acceleration of the successor activity.D. A lead allows an acceleration of the successor activity. | Show Answer | D. A lead allows an acceleration of the successor activity.
PMP Question 132 | Which of the following is not a Tuckman’s team development stage? | A. ConfrontingB. FormingC. NormingD. Adjourning | Show Answer | A. Confronting | Tagged with Adjourning Confronting Forming Norming Tuckman | Tagged with Adjourning Confronting Forming Norming Tuckman
PMP Question 133 | A first-time project manager was of the opinion that all training activities need to be planned. He discussed this with an experienced project manager, and understood that some training was necessarily unplanned. Which of the following correctly lists examples of unplanned training? | A. Training by observation, conversation, and project management appraisalsB. Training by mentoring, on-the-job training, and online coursesC. Training by conversation, coaching, and classroom trainingD. Training by mentoring, observation, and coaching | Show Answer | A. Training by observation, conversation, and project management appraisals
PMP Question 134 | Two of your expert team members have been in a heated argument over the use of a new software product for your research project. Recently you noticed that the argument instead of increasing creativity, is causing conflict between the team members. To prevent the conflict from escalating, you want to resolve it by evaluating alternatives and open dialogue. All of the following statements about a conflict are false EXCEPT: | A. Scarce resource cannot be a source of a conflict.B. Conflict is inevitable in a project environment.C. Personal work style cannot be a source of a conflictD. Reducing the amount of conflict is not desirable. | Show Answer | B. Conflict is inevitable in a project environment.
PMP Question 135 | The WBS structure can be created in a number of forms except which of the following? | A. Using work packages as the second level of decomposition, with the project deliverables inserted at the third level.B. Using major deliverables as the second level of decomposition.C. Using phases of the project life cycle as the second level of decomposition, with the product and project deliverables inserted at the third level.D. Using subcomponents which may be developed by organizations outside the project team, such as contracted work. | Show Answer | A. Using work packages as the second level of decomposition, with the project deliverables inserted at the third level.
PMP Question 136 | Visiting a construction site to ensure the work being done is the same work called out in the requirements is called: | A. MilestoneB. Scope validationC. Variance AnalysisD. Requirements traceability | Show Answer | B. Scope validation | Tagged with Milestone Scope validation Variance analysis | Tagged with Milestone Scope validation Variance analysis
PMP Question 137 | If you are influencing factors that create changes to the cost of the project, which process are you using? | A. Negotiate CostsB. Estimate CostsC. Control CostsD. Determine Budget | Show Answer | C. Control Costs | Tagged with Determine Budget Estimate Costs | Tagged with Determine Budget Estimate Costs
PMP Question 138 | In the earned value management technique, the cost performance baseline is referred to as: | A. Cost Measurement Baseline (CMB)B. Performance Measurement Baseline (PMB)C. Performance Base Value (PBV)D. Performance Cost Baseline (PCB) | Show Answer | B. Performance Measurement Baseline (PMB) | Tagged with Cost Measurement Baseline (CMB) Performance Base Value (PBV) Performance Cost Baseline (PCB) Performance Measurement Baseline (PMB) | Tagged with Cost Measurement Baseline (CMB) Performance Base Value (PBV) Performance Cost Baseline (PCB) Performance Measurement Baseline (PMB)
PMP Question 139 | A project manager wishes to illustrate the connections between the work that needs to be done and the project team members. According to the PMBOK, the resulting document would be called: | A. Responsibility Assignment Matrix (RAM)B. Resource Planning Chart (RPC)C. Task Assignment Model (TAM)D. Resource Assignment Chart (RAC) | Show Answer | A. Responsibility Assignment Matrix (RAM) | Tagged with Resource Assignment Chart (RAC) Resource Planning Chart (RPC) Responsibility Assignment Matrix (RAM) Task Assignment Model (TAM) | Tagged with Resource Assignment Chart (RAC) Resource Planning Chart (RPC) Responsibility Assignment Matrix (RAM) Task Assignment Model (TAM)
PMP Question 140 | You are defining the schedule activities for your project and identifying deliverables at the lowest level in the Work Breakdown Structure (WBS). You find that there is insufficient definition of the project scope to decompose a branch of the WBS down to the work package level. You now look at using the last component in that branch of the WBS to develop a high-level project schedule for that component. Such a planning component is called: | A. A planning packetB. Control systemC. A planning packageD. Control element | Show Answer | C. A planning package | Tagged with Control element planning package Work Breakdown Structure (WBS) | Tagged with Control element planning package Work Breakdown Structure (WBS)
PMP Question 141 | If you had an experience with a particularly good or poor performing vendor, what is the correct way to document this experience for future projects? | A. Create a seller performance evaluationB. Call the vendor and talk to them about the experienceC. Tell all your friends about itD. Vow to only work with that vendor from now on | Show Answer | A. Create a seller performance evaluation
PMP Question 142 | Your have recently finished an advanced project management training course that was paid for by your project budget. Because the budget for your project is not large enough to train any other resources on the project, your manager has asked you to make copies of the course materials and distribute them to the rest of the staff. What do you do? | A. Make the copies.B. Provide a single copy of the materials.C. Scan the materials and place them on the corporate intranet for easy access.D. Refuse the request. | Show Answer | D. Refuse the request.
PMP Question 143 | Defense Dynamics has been awarded a fixed price project to design and build a military cargo jet. The design team is looking at ways to increase the cargo capacity of the plane while keeping manufacturing costs and the fuel efficiency of the final product within specific limits. The engineers on this team have identified factors that affect capacity, costs, and fuel efficiency and have created a statistical model of how these factors impact each other. The outcome of this model is a design with the highest cargo capacity and fuel efficiency at the lowest cost possible. What type of mathematical model is this called? | A. Outcome-based HypothesisB. Basis BenchmarkingC. Cost of QualityD. Design of Experiments | Show Answer | D. Design of Experiments | Tagged with Basis Benchmarking Design of experiments mathematical model Outcome-based Hypothesis | Tagged with Basis Benchmarking Design of experiments mathematical model Outcome-based Hypothesis
PMP Question 144 | Close Project or Phase is the process of completing and concluding all activities across all process groups to officially close the project. Which of the following activities are NOT performed during this process? | A. Actions required to transfer completed products to operationsB. Actions required to archive project informationC. Actions required to audit project success or failureD. Actions required to accept the deliverables | Show Answer | D. Actions required to accept the deliverables | Tagged with deliverables | Tagged with deliverables
PMP Question 145 | You are assisting another project manager interview candidates for a resource position on his project. While reviewing your interview notes together, the other project manager sorts the candidate’s resumes into two groups: one for further interviews, the other for candidates that did not meet the requirements for the position. You notice that he has placed several of the highly qualified candidates in the second pile, stating that those interviewees “did not fit the corporate profile.” Upon further review, you discover that these candidates are all of the same ethnic group. What do you do? | A. Excuse yourself from the interviewing process.B. Report this to the appropriate management.C. File a complaint with PMID. Do nothing. | Show Answer | B. Report this to the appropriate management. | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 146 | Which of the following is neither an input nor an output of the Direct and Manage Project Work process? | A. Approved change requestsB. Change requestsC. Approved deliverablesD. Deliverables | Show Answer | C. Approved deliverables
PMP Question 147 | Peter is a project manager handling an Alternate water-supply project. During a project performance review, he notices the following: (i) Activity A, on the critical path, is delayed by 4 days. (ii) Activity B, not on the critical path, is delayed by 9 days. (iii) Activity C, on the critical path is delayed by 2 days (iv) Activity D, not on the critical path, is delayed by 5 days. | In what sequence should Peter prioritize his efforts in addressing these delays? |  | B. Activity A, Activity C, Activity B, Activity D | Tagged with critical path | Tagged with critical path
PMP Question 148 | To assist with the selection of a supplier for a large procurement on your project, you’ve hired a consultant. The consultant has prepared an independent estimate to be used as a benchmark while reviewing bids on the RFP. The independent estimate is confidential and is not shared with any bidders. When the sealed bids are opened, you discover that only 1 supplier, has submitted a quote lower than the independent estimate. All other quotes are 45% to 70% higher than the benchmark. While discussing this development with members of the project team, you learn that the company with the lowest bids is owned by a distant relative of the consultant you hired to create the benchmark. What is the best course of action? | A. Confirm that the lowest bidder has understood the requirements and award them the contract’.B. Since one of the supplier knows more than others, you must disclose the independent estimate to all others to be fair.C. Disqualify the lowest bidder.D. Review the RFP specifications and requirements. | Show Answer | D. Review the RFP specifications and requirements. | Tagged with benchmark RFP specifications | Tagged with benchmark RFP specifications
PMP Question 149 | During the planning phase of your project, your team decided to procure a certain brand of hardware because it had the lowest price and free shipping and installation. This approach saved $6,000 over the other brands being considered. Since that purchase, however, it has been discovered that the annual maintenance costs for this hardware are $2,500 per year, and $12,500 over the life of the hardware. These costs were not budgeted in the project, nor were they included in the TCO analysis that was done as part of the project business case. What should you do? | A. Request a new budget.B. Notify the stakeholders immediately.C. Revise the business case.D. Do nothing. This will not impact the project budget. | Show Answer | B. Notify the stakeholders immediately. | Tagged with TCO analysis | Tagged with TCO analysis
PMP Question 150 | You are in a meeting with your senior manager who has been helping you to organize and manage a team of IT people with numerous backgrounds. While you are discussing the creativity and breakthrough performance your team is demonstrating now, your senior manager indicates that your team has moved from the storming to the performing stage. Which of the following explains the characteristic of the performing stage? | A. In the performing stage, the team completes the work and disbands as a project teamB. In the performing stage, the team function as a well organized unit and resolve issues effectivelyC. In the performing stage, the team members are not collaborativeD. In the performing stage, the team starts to work together and adjust their behaviors | Show Answer | B. In the performing stage, the team function as a well organized unit and resolve issues effectively | Tagged with Bruce Tuckman norming stage performing stage storming stage | Tagged with Bruce Tuckman norming stage performing stage storming stage
PMP Question 151 | In an ongoing project, the project sponsor and a manager of the performing organization are having conflicts. What would be your comment on this situation? | A. The project manager needs to step in and handle the stakeholders’ expectations. The stakeholders may have different objectives and interests in the project.B. The project manager needs to step in and handle the stakeholders’ expectations. All stakeholders are supposed to have the same objectives and interests in a project.C. The project manager should resolve in favor of the project sponsor since he is providing the funds for the project.D. The project manager should resolve in favor of the manager of the performing organization since they are executing the project and need to be kept in good books. | Show Answer | A. The project manager needs to step in and handle the stakeholders’ expectations. The stakeholders may have different objectives and interests in the project.
PMP Question 152 | The project management plan can best be described as: | A. A list of tasks, activities, durations and resources in a software program (e.g., Microsoft Project)B. Coordinating changes across the entire projectC. Integrating and coordinating all project plans to create a consistent, coherent documentD. Integrating and coordinating all project documents and stakeholder expectations | Show Answer | C. Integrating and coordinating all project plans to create a consistent, coherent document
PMP Question 153 | As the Project Manager for Midway Carnival Rides, you are starting off on the Define Scope process. Which of the following is a key input to the process? | A. Risk Management PlanB. Quality Management PlanC. Project CharterD. Staffing Management Plan | Show Answer | C. Project Charter | Tagged with Quality Management Plan | Tagged with Quality Management Plan
PMP Question 154 | As project manager, you scheduled a status update meeting. During the meeting, a problem developed and the group discussed it. The day after the meeting, Kevin approached you and expressed his concern that the problem was not really resolved. After thinking about it, he felt that his concerns were still valid and should be addressed. What conflict resolution method was likely used at the status meeting? | A. SmoothingB. ForcingC. WithdrawalD. Collaboration | Show Answer | A. Smoothing
PMP Question 155 | A technique that calculates multiple project durations with different sets of activity assumptions and variables is called: | A. Process analysisB. Theoretical AnalysisC. SimulationD. Effect Analysis | Show Answer | C. Simulation | Tagged with Effect Analysis Simulation Theoretical Analysis | Tagged with Effect Analysis Simulation Theoretical Analysis
PMP Question 156 | During a discussion with the quality department, a project manager was given to understand that both prevention and inspection meant the same as applied to projects. However, he had a different understanding of the terms. What would you comment on this situation? | A. The project manager is correct. Prevention is about keeping errors out of the process whereas inspection is about keeping errors out of the hands of the customer.B. The project manager is correct. Inspection is about keeping errors out of the process whereas prevention is about keeping errors out of the hands of the customer.C. The project manager is wrong. Both inspection and prevention are about keeping errors out of the hands of the customer. They are used in different contexts.D. The project manager is wrong. Both inspection and prevention are about keeping errors out of the process. They are used in different contexts. | Show Answer | A. The project manager is correct. Prevention is about keeping errors out of the process whereas inspection is about keeping errors out of the hands of the customer.
PMP Question 157 | Peter, a project manager, is updating the status of his project. Based on the performance indices, he expects the project to finish a month earlier than the planned finish date. However, he expects the project to exceed the budgeted costs. What can you say about the schedule performance index (SPI) of the project? | A. The SPI is less than 1.0.B. The SPI equals the CPI.C. The SPI is greater than 1.0.D. The SPI is equal to 1.0. | Show Answer | C. The SPI is greater than 1.0. | Tagged with Schedule Performance Index (SPI) | Tagged with Schedule Performance Index (SPI)
PMP Question 158 | You are managing a project for a customer that has just gone bankrupt and is subject to liquidation proceedings. There are several outstanding invoices that this customer has not paid to your company. What should you do now? | A. Go into alternate dispute resolutionB. Do nothing.C. Contact the appropriate management at your company for advice how to proceed.D. Send the invoices to the bankruptcy attorneys. | Show Answer | C. Contact the appropriate management at your company for advice how to proceed.
PMP Question 159 | Prioritization matrices are an important quality planning tool. They provide a way of ranking a diverse set of problems and/or issues by order of importance. How is this list usually generated? | A. Through control chartsB. Through PERT analysisC. Through brainstormingD. Through variance analysis | Show Answer | C. Through brainstorming | Tagged with brainstorming PERT analysis Prioritization matrices | Tagged with brainstorming PERT analysis Prioritization matrices
PMP Question 160 | When a project is performed under contract, the contractual provisions will generally be considered as for the project. | A. ConstraintsB. ExclusionsC. DeliverablesD. Provisions | Show Answer | A. Constraints
PMP Question 161 | A project manager is considering risk in a project. When does risk come into play in a project? | A. During the SWOT (strengths, weaknesses, opportunities, and threats) analysis.B. During the Identify Risks phase.C. As soon as the Plan Risk Management phase beginsD. As soon as a project is conceived | Show Answer | D. As soon as a project is conceived
PMP Question 162 | During a work breakdown structure meeting you have decomposed the deliverables into work packages and created your WBS dictionary. However, you now want to decompose the work packages to assist you in estimating, executing and control the project. These decomposed work packages are called? | A. Work Packages can’t be decomposed into smaller unitsB. ActivitiesC. MilestonesD. Control Accounts | Show Answer | B. Activities | Tagged with WBS dictionary work breakdown structure | Tagged with WBS dictionary work breakdown structure
PMP Question 163 | You have assembled a group of subject matter experts (SMEs) to perform an exercise where they are going to complete a probability and impact matrix chart. You and your team are still in what process group? | A. RiskB. Monitor and ControllingC. Quantitative AnalysisD. Planning | Show Answer | D. Planning | Tagged with subject matter experts (SMEs) | Tagged with subject matter experts (SMEs)
PMP Question 164 | A project risk manager distributes anonymous questionnaires to project team members to help identify risks. This is called . | A. Game TheoryB. The Consensus MethodC. InterviewingD. The Delphi Technique. | Show Answer | D. The Delphi Technique.
PMP Question 165 | A project manager had scheduled a number of training programs for his team. However, he was aware that apart from planned training, unplanned training also took place in a number of ways. Which of these is not one of the ways in which unplanned training can happen? | A. ClassroomB. ObservationC. Project performance appraisalsD. Conversation | Show Answer | A. Classroom
PMP Question 166 ( PMBOK 6th edition ) | A new CEO has come into your company and has promptly shut down your project because it no longer met the business needs of the company. While not pleased with the decision, you document the level and completeness of the project to date. What activity or process is this part of? | A. Close Project or PhaseB. Manage Project KnowledgeC. Control ScopeD. Validate Scope | Show Answer | A. Close Project or Phase | Tagged with Close Procurements Manage Project Knowledge | Tagged with Close Procurements Manage Project Knowledge
PMP Question 167 ( PMBOK 6th edition ) | Which of the following processes will determine the correctness of deliverables? | A. Plan Quality AssuranceB. Plan Quality ManagementC. Control QualityD. Manage Quality | Show Answer | C. Control Quality | Tagged with Manage Quality Perform Quality Assurance | Tagged with Manage Quality Perform Quality Assurance
PMP Question 168 | A team member in your project is constantly providing incomplete deliverables and not performing well. What should you do first? | A. Discuss the issue with the team member in privateB. Discuss the issue with the team member in presence of the project sponsorC. Discuss the issue with the team member in the presence of other team membersD. Discuss the issue with the team member in presence of the company’s HR manager | Show Answer | A. Discuss the issue with the team member in private
PMP Question 169 | Under which of the following scenarios would you not use a Decision tree? | A. When some future scenarios are unknown.B. When you need to look at the implications of not choosing certain alternatives.C. When the future scenarios are known.D. When the outcomes of some of the actions are uncertain. | Show Answer | C. When the future scenarios are known. | Tagged with Decision tree | Tagged with Decision tree
PMP Question 170 | As part of the Develop Team process, the project manager of a project has planned for some Team Building activities. Team Building Activities should take place throughout the project life cycle, but have greater benefit when conducted: | A. On a need-basis.B. At the end of the project life cycleC. Early in the project life cycleD. In the middle of the project life cycle. | Show Answer | C. Early in the project life cycle | Tagged with Develop Team process Team Building | Tagged with Develop Team process Team Building
PMP Question 171 | Jane is the project manager of large project. During the Determine Budget process, she identifies that contingency reserves need to be made for unplanned but potentially required changes that could result from realized risks identified in the risk register. Which of the following is true about reserves? | A. Management Reserves are not a part of project cost baseline, but will be included in the total budget for the projectB. Contingency Reserves are not a part of project cost baseline, but will be included in the total budget for the projectC. Both the Management Reserves and the Contingency Reserves are not part of project cost baseline, and they are also not included in the total budget for the projectD. Both the Management Reserves and the Contingency Reserves are not part of project cost baseline, but they are included in the total budget for the project | Show Answer | A. Management Reserves are not a part of project cost baseline, but will be included in the total budget for the project | Tagged with contingency reserves cost baseline Determine Budget process Management Reserves Risk Register | Tagged with contingency reserves cost baseline Determine Budget process Management Reserves Risk Register
PMP Question 172 | Which of the following best describes the Validate Scope process? | A. Validating that the project quality requirements have been metB. Controlling changes to the scope of the projectC. Obtaining stakeholders’ formal acceptance of the project deliverablesD. Validating that all of the project’s objectives have been met | Show Answer | C. Obtaining stakeholders’ formal acceptance of the project deliverables
PMP Question 173 | The key difference between Validate Scope and Control Quality is: | A. Validate Scope is concerned with meeting the quality standards specified.B. Validate Scope is concerned with the acceptance of deliverables.C. Validate Scope does not apply in projects that have been cancelled.D. Validate Scope can never be performed in parallel with quality control. | Show Answer | B. Validate Scope is concerned with the acceptance of deliverables. | Tagged with Control Quality Validate Scope | Tagged with Control Quality Validate Scope
PMP Question 174 ( PMBOK 6th edition ) | You have just returned from the weekly change control board meeting where you presented the requested changes to the employee move project. You had five change requests approved, however one rejected request. These are outputs of what process? | A. Control QualityB. Control ScopeC. Monitor RisksD. Perform Integrated Change Control | Show Answer | D. Perform Integrated Change Control | Tagged with Control Risks Monitor Risks Perform Integrated Change Control | Tagged with Control Risks Monitor Risks Perform Integrated Change Control
PMP Question 175 | In a Cause and Effect diagram, which of these is not a potential cause? | A. PersonnelB. Problem statementC. TimeD. Material | Show Answer | B. Problem statement | Tagged with Cause and Effect diagram | Tagged with Cause and Effect diagram
PMP Question 176 | The project manager in charge of a new credit card software project has asked the product manager to create a checklist to assist with the identification of risks. A risk checklist can be created from which of the following sources? | A. Agreement templatesB. Earned value measurementsC. Project Management Information SystemD. The lowest level of the Risk Breakdown Structure | Show Answer | D. The lowest level of the Risk Breakdown Structure | Tagged with Earned value measurements Risk Breakdown Structure risk checklist | Tagged with Earned value measurements Risk Breakdown Structure risk checklist
PMP Question 177 | Which of the following quality control tools and techniques may not be used for root cause analysis? | A. Fishbone diagramB. Scatter diagramC. Ishikawa diagramD. Cause and effect diagram | Show Answer | B. Scatter diagram | Tagged with Fishbone diagram Ishikawa diagram Scatter diagram | Tagged with Fishbone diagram Ishikawa diagram Scatter diagram
PMP Question 178 | Which of the following is neither an input to nor an output of the Develop Project Charter process? | A. A project charterB. Professional and technical associationsC. A business caseD. A project statement of work | Show Answer | B. Professional and technical associations
PMP Question 179 | You have been asked to establish a project charter for your new project. According to PMBOK, who normally has the responsibility to authorize the charter? | A. Company president or CEOB. Project initiator or sponsorC. Key project stakeholdersD. Project manager | Show Answer | B. Project initiator or sponsor
PMP Question 180 | Emily’s project is in execution. Emily is currently planning to execute the Manage Stakeholder Engagement process. She has gathered the stakeholder management plan, the recent change log, and the necessary organizational process assets. Which of the following is a key input to this process that is still missing from this list? | A. Communications methodsB. Stakeholder registerC. Stakeholder management strategyD. Communications management plan | Show Answer | D. Communications management plan | Tagged with stakeholder | Tagged with stakeholder
PMP Question 181 | A contract change control system should include: | A. Vendor contact information, tracking systems, and approval levels necessary for authorizing changesB. Paperwork, tracking systems, dispute resolution procedures, and approval levels necessary for authorizing changesC. Information database, dispute resolution procedures, and approval levels necessary for authorizing changesD. Tracking systems, legal ramifications for certain actions, and approval levels necessary for authorizing changes | Show Answer | B. Paperwork, tracking systems, dispute resolution procedures, and approval levels necessary for authorizing changes | Tagged with authorizing changes dispute resolution | Tagged with authorizing changes dispute resolution
PMP Question 182 | As a project manager based at the customer location for a performing organization, you strike up a rapport with a customer manager. As the project progresses, the manager asks you to make certain changes to the project scope and wants this to be handled on an informal basis. You should: | A. Contact your manager in your organization and ask for this work to be done without payment, as a goodwill gesture.B. Comply with the manager’s request. It is important to continue to maintain a good relationship with the manager.C. Refuse to take up any changes since the manager has asked you to do it informally.D. Explain to the manager that you would need to formally document these as part of project scope change and put it through the change management process. | Show Answer | D. Explain to the manager that you would need to formally document these as part of project scope change and put it through the change management process.
PMP Question 183 | Variance Analysis is an important tool used in the Control Costs Process. Which of the following statements regarding variances is correct? | A. The percentage range of acceptable variances will tend to increase as more work is accomplishedB. The percentage range of acceptable variances will tend to decrease as more work is accomplishedC. The percentage range of acceptable variances is high at the start of a project, tends to decrease in the middle of a project, and then tends to increase as the project nears completionD. The percentage range of acceptable variances is a constant all through the project | Show Answer | B. The percentage range of acceptable variances will tend to decrease as more work is accomplished | Tagged with Variance analysis | Tagged with Variance analysis
PMP Question 184 | What is the BEST tool and technique that provides the expected cost of a procurement and helps identify significant variations from cost estimates prepared in-house? | A. Screening systemB. Bidder conferencesC. Independent estimatesD. Buyer-conducted performance review | Show Answer | C. Independent estimates | Tagged with Bidder conferences Independent Estimates Plan procurement management Screening system | Tagged with Bidder conferences Independent Estimates Plan procurement management Screening system
PMP Question 185 | Analyzing the situation, differentiating between wants and needs, and focusing on interests and issues rather than on positions are critical elements in: | A. Project CharterB. EstimatingC. Variance analysisD. Negotiating | Show Answer | D. Negotiating | Tagged with Estimating Negotiating project charter Variance analysis | Tagged with Estimating Negotiating project charter Variance analysis
PMP Question 186 | Which of the following is not an enterprise environmental factor influencing the Develop Project Management Plan process? | A. Project management body of knowledgeB. Governmental or industry standardsC. Project Management Plan templateD. Project management information system | Show Answer | C. Project Management Plan template | Tagged with Project management information system project management plan template | Tagged with Project management information system project management plan template
PMP Question 187 | You are reviewing the responses to an RFP issued by your company and realize that a major requirement was not included in the RFP that was released. By chance, however, one of the bidders included that requirement in their response. What is the best course of action? | A. Award the contract to that bidder.B. Revise and reissue the RFP.C. Select the bid that included the requirement.D. Cancel the RFP. | Show Answer | B. Revise and reissue the RFP.
PMP Question 188 | Which of the following is not an example of a work performance report? | A. Status reportB. Project charterC. Project update memoD. Project recommendations | Show Answer | B. Project charter
PMP Question 189 | The selection of life cycle for the project, the processes to be applied to each phase, and the results of the tailoring by the project management team are usually found in the: | A. Project scope statementB. Project management planC. Project scheduleD. Project charter | Show Answer | B. Project management plan | Tagged with project charter project management plan Project schedule Project Scope Statement | Tagged with project charter project management plan Project schedule Project Scope Statement
PMP Question 190 | Which of the following processes produces a work breakdown structure as an output? | A. Create WBSB. Define ScopeC. Develop Project Management PlanD. Define Activities | Show Answer | A. Create WBS | Tagged with Create WBS Define Activities | Tagged with Create WBS Define Activities
PMP Question 191 | Organizational process assets are key inputs to the Manage Stakeholder Engagement process. The key elements of the organizational process assets utilized during this process are organizational communication requirements, issue management procedures and the change control procedures. Which of the following is also a key organizational process asset that must be considered during this process? | A. Process audit proceduresB. Human resource policiesC. Historical information about previous projectsD. Project document templates | Show Answer | C. Historical information about previous projects
PMP Question 192 | As part of the Risk Response planning for your project, you are trying to come up with a strategy to deal with negative risks or threats. In order to eliminate the impact of a particular risk, you relax the objective that is in jeopardy by extending the project schedule. This is an example of | A. TransferenceB. MitigationC. AvoidanceD. Postponement | Show Answer | C. Avoidance
PMP Question 193 | There is a heavy demand for new houses in your city’s expensive neighborhood. RECON, a construction company employed you as a project manager to assess the benefit of building new energy efficient houses in that neighborhood although it takes more expensive technology to build such houses. You have started gathering data to perform the detail payback analysis to submit a report to the management. Since the full financial impact of energy efficient house building is difficult to estimate, you would like to prepare a rough cost-benefit analysis and include it with the report. Which of the following describes the effort you are undertaking in this scenario? | A. You are developing a business case to provide as an input to the develop project charter processB. You are developing a cost management plan to provide as an input to the estimate costs processC. You are developing a risk management plan to provide as an input to the perform quantitative risk analysis processD. You are developing a cost-benefit analysis to provide as an input to the plan risk management process | Show Answer | A. You are developing a business case to provide as an input to the develop project charter process | Tagged with cost management plan | Tagged with cost management plan
PMP Question 194 | If you are writing a proposal for additional funding, which communication style should you choose? | A. formal and horizontalB. formal and verticalC. informal and verticalD. informal and horizontal | Show Answer | B. formal and vertical
PMP Question 195 | A summary milestone schedule would normally be part of which document? | A. Project sign-off documentB. Project charterC. Project requirements documentD. Project scope statement | Show Answer | B. Project charter | Tagged with funnel distribution | Tagged with funnel distribution
PMP Question 196 | Your company has just completed an unexpected round of layoffs. Morale is low, and resources are tighter than ever. Your project is now behind schedule because of the loss of resources. Overtime work will be required of everyone for the next several weeks in order to close the gap. One of the critical resources on your project has an upcoming vacation that was approved and scheduled months ago. However, without this resource you will be unable to get back on schedule. What do you do? | A. Notify the project stakeholders of the situation immediately.B. Cancel all vacations.C. Find another resource.D. Compress the schedule further. | Show Answer | A. Notify the project stakeholders of the situation immediately.
PMP Question 197 | A project manager uses a Power / Interest grid to identify stakeholders in the project and to manage their expectations. Identify which of the following statements is wrong in the context of a Power / Interest grid. | A. Stakeholders with lower power and lower interest need to be monitored.B. Stakeholders with higher power and lower interest need to kept satisfied.C. Stakeholders with lower power and higher interest need to be kept informedD. Stakeholders with higher power and higher interest need the least attention. | Show Answer | D. Stakeholders with higher power and higher interest need the least attention.
PMP Question 198 | You find out that a project team member has been stealing some material from the work place. You accidentally discover this and he says that he is very sorry about it, and will not repeat it again. You will: | A. Get a statement in writing from the project team member saying that he will not repeat such an activity.B. Document the matter for your archives.C. Inform your HR department about the matterD. Keep quiet until it repeats for a second time | Show Answer | C. Inform your HR department about the matter | Tagged with Ethical Issue project team member | Tagged with Ethical Issue project team member
PMP Question 199 | As part of Define Activities, you are looking at dependencies used to define the sequence among the activities. Which of these is not a valid type of dependency? | A. Linked dependencyB. External dependencyC. Discretionary dependencyD. Mandatory dependency | Show Answer | A. Linked dependency | Tagged with dependency Mandatory dependency | Tagged with dependency Mandatory dependency
PMP Question 200 ( PMBOK 6th edition ) | Which of these processes is NOT a Project Schedule Management process? | A. Create WBSB. Develop ScheduleC. Define ActivitiesD. Sequence Activities | Show Answer | A. Create WBS | Tagged with Develop Schedule PMBOK 6th edition Project Schedule Management process Project Time Management process Sequence Activities WBS | Tagged with Develop Schedule PMBOK 6th edition Project Schedule Management process Project Time Management process Sequence Activities WBS