## Sheet1
title | Field2 | Field3 | Field4 | Field5 | Field6 | Field7
PMP Question 3 | You work as an engineer for a large engineering firm. The last week you have been corresponding back and fourth with the supervisor of your department about the horizontal stabilizers required for the wings on a new aircraft you are designing. Which communication dimension does this represent? | A. HorizontalB. FormalC. ExternalD. Vertical | Show Answer | D. Vertical | Tagged with communication dimension | Tagged with communication dimension
PMP Question 4 | Many organizations treat contract administration as an administrative function separate from the project organization. Who carries out the function of contract administration in such organizations? | A. The Project ManagerB. The Procurement AdvisorC. The Procurement AdministratorD. The Contract Advisor | Show Answer | C. The Procurement Administrator | Tagged with Procurement Administrator Procurement Advisor | Tagged with Procurement Administrator Procurement Advisor
PMP Question 5 | A project team collects project work performance data and transforms that into work performance information for the key project stakeholders on a monthly basis. Which of the following does not provide a good platform to share this information with the stakeholders? | A. Project file updatesB. Project update meetingsC. Information management systemD. Status review meetings | Show Answer | A. Project file updates | Tagged with key project stakeholders Status review meetings | Tagged with key project stakeholders Status review meetings
PMP Question 6 | John is the project manager of a project that is in an early phase. He needs to estimate costs but finds that he has a limited amount of detailed information about the project. Which of the following estimation techniques would be least suited to his requirements? | A. Top-down EstimatingB. Bottom-up EstimatingC. Analogous EstimatingD. Budgetary Estimating | Show Answer | B. Bottom-up Estimating | Tagged with Analogous Estimating Bottom-up Estimating Budgetary Estimating Top-down Estimating | Tagged with Analogous Estimating Bottom-up Estimating Budgetary Estimating Top-down Estimating
PMP Question 7 | Peter is managing a software development project for the first time. He is facing issues with scheduling meetings with the senior project managers at the company as they are extremely busy with their current assignments. Peter needs to understand what went right and wrong on previous similar projects so that he can manage his project better. In this situation, what should Peter do? | A. Review the project’s business case for details.B. Request key stakeholders to help schedule these coaching meetings.C. Review lessons learned from the past similar projects.D. Review the project charter for details. | Show Answer | C. Review lessons learned from the past similar projects. | Tagged with coaching meetings | Tagged with coaching meetings
PMP Question 8 | You have been asked to determine the logical relationships, leads, and lags for the activities that make up a project. What would be the BEST technique to use? | A. Resource SmoothingB. Critical Path MethodC. What-If scenario analysis.D. Resource Leveling | Show Answer | B. Critical Path Method | Tagged with Critical Path Method Resource Leveling Resource Smoothing What-If scenario analysis | Tagged with Critical Path Method Resource Leveling Resource Smoothing What-If scenario analysis
PMP Question 9 | A statement of work (SOW) is a narrative description of the products or services to be delivered by the project. It usually references all of the following except: | A. The business caseB. The product scope descriptionC. The strategic planD. The business need | Show Answer | A. The business case | Tagged with business case statement of work (SOW) strategic plan | Tagged with business case statement of work (SOW) strategic plan
PMP Question 10 | The Conduct Procurements process receives bids or proposals and applies criteria to select one or more sellers who are both qualified and acceptable as a seller. Which of the following techniques is not a valid technique for this process? | A. Make-or-buy analysisB. Proposal Evaluation TechniquesC. AdvertisingD. Bidder Conference | Show Answer | A. Make-or-buy analysis | Tagged with Advertising Bidder Conference Conduct Procurements process Make-or-buy analysis Proposal Evaluation Techniques | Tagged with Advertising Bidder Conference Conduct Procurements process Make-or-buy analysis Proposal Evaluation Techniques
PMP Question 11 | John is in the process of preparing the project performance report for the team meeting. He is expecting many questions from his stakeholders on the budget and schedule. He calculates the following values; Budget at Completion (BAC) = $22,000, Earned Value (EV) = $13,000, Planned Value (PV) = $ 14,000, Actual cost (AC) = $15,000. | What is the Estimate at Completion (EAC) for the project if the work is performed at the budgeted rate? |  | A. $24,000 – If the project work is performed at the budgeted rate, the Estimation at Completion can be determined using the formula (EAC) = AC + (BAC – EV) | Tagged with Actual cost Budget at Completion Earned Value Estimate at Completion Estimate at Completion (EAC) Planned Value | Tagged with Actual cost Budget at Completion Earned Value Estimate at Completion Estimate at Completion (EAC) Planned Value
PMP Question 12 | Your team has built an exotic sports car for a wealthy client. Every deliverable has been verified by the project team against the quality requirements and accepted by the client. Now the Project Manager is reviewing the car to ensure it meets the specifications of the client, as agreed to in the project plan. What project management process is represented here? | A. ClosingB. Monitoring and ControllingC. PlanningD. Execution | Show Answer | A. Closing | Tagged with Closing Execution Monitoring and Controlling Planning | Tagged with Closing Execution Monitoring and Controlling Planning
PMP Question 13 | You are a Project Manager for an automotive parts company. Your organization has been hired to produce clutches for an exotic car company which will involve the design and production of custom clutches. During the course of the project you are reviewing a quality control statistics chart that examines every clutch produced for the month and notice several cases where the spring component of the clutch is expanding with too much force and is falling outside the upper control limit. Which type of Quality Control tool are you MOST LIKELY making use of? | A. Control chartsB. Statistical SamplingC. Cause and Effect diagramD. Precedence Diagramming Method | Show Answer | A. Control charts | Tagged with Cause and Effect diagram Control charts Precedence Diagramming Method Quality Control tool Statistical Sampling | Tagged with Cause and Effect diagram Control charts Precedence Diagramming Method Quality Control tool Statistical Sampling
PMP Question 14 | Which of the following Project Scope Management processes documents a configuration management system? | A. Control ScopeB. Define ScopeC. Verify ScopeD. Plan Scope Management | Show Answer | D. Plan Scope Management | Tagged with Control Scope Define Scope Plan Scope Management | Tagged with Control Scope Define Scope Plan Scope Management
PMP Question 15 | As a project manager based at the customer location for a performing organization, you strike up a rapport with a customer manager. As the project progresses, the manager asks you to make certain changes to the project scope and wants this to be handled on an informal basis. You should: | A. Contact your manager in your organization and ask for this work to be done without payment, as a goodwill gesture.B. Comply with the manager’s request. It is important to continue to maintain a good relationship with the manager.C. Refuse to take up any changes since the manager has asked you to do it informally.D. Explain to the manager that you would need to formally document these as part of project scope change and put it through the change management process. | Show Answer | D. Explain to the manager that you would need to formally document these as part of project scope change and put it through the change management process. | Tagged with Ethics goodwill gesture | Tagged with Ethics goodwill gesture
PMP Question 16 | When developing your project schedule, you have asked everyone to provide a list of planned vacations over the next 3 months and you have applied this into the tasks that each person is responsible for. This is an example of what tool? | A. Resource CalendarsB. Adjusting LeadsC. Schedule VariancesD. Adjusting Lags | Show Answer | A. Resource Calendars | Tagged with Adjusting Lags Adjusting Leads Resource Calendars Schedule Variances | Tagged with Adjusting Lags Adjusting Leads Resource Calendars Schedule Variances
PMP Question 17 | You have been asked to create a graphical display of schedule-related information listing schedule activities on the left side of the chart, dates on the top, and activity durations as date-placed horizontal bars on the right side. What would such a chart be called? | A. PERT chartB. Gantt chartC. Hunt chartD. GERT chart | Show Answer | B. Gantt chart | Tagged with Gantt chart PERT chart | Tagged with Gantt chart PERT chart
PMP Question 18 ( PMBOK 6th edition ) | A key output of Plan Resource Management is a list of project roles and responsibilities. What should this document include? | A. Work packages, Effort, Authority, DutiesB. Role, Responsibility, Authority, RiskC. Role, Title, Resource Cost, ResponsibilityD. Role, Authority, Responsibility, Competency | Show Answer | D. Role, Authority, Responsibility, Competency | Tagged with Plan Human Resource Management Plan Resource Management | Tagged with Plan Human Resource Management Plan Resource Management
PMP Question 19 | The legal nature of the contractual relationship between a buyer and a seller requires that appropriate legal counsel be involved in the project, for specific activities. Which of the following phases requires legal counsel to be involved. | A. Control procurementsB. Plan procurement managementC. Conduct procurementsD. Each procurement management process | Show Answer | D. Each procurement management process | Tagged with Control procurements Plan procurement management | Tagged with Control procurements Plan procurement management
PMP Question 20 | All of the following are components of an effective change control, EXCEPT: | A. Variance analysisB. Expert judgmentC. Change control toolsD. Meetings | Show Answer | A. Variance analysis | Tagged with Change control tools Expert judgment Variance analysis | Tagged with Change control tools Expert judgment Variance analysis
PMP Question 21 | A first-time project manager decided that he would have a ‘perfect project’. He informed the customer that this project would not accept change requests of any kind and the scope would need to be detailed out accurately right at the start of the project. The customer agreed to this request. What would your comment on this situation be? | A. The is a good example of how the project management team can decide what is and what is not necessary for the project. Not allowing changes is a good way of ensuring that the project meets requirements as detailed out in project scope.B. This is unrealistic and impractical. Change is inevitable and rather than look at a ‘no change’ project, it would be more in the project interests to plan for a robust change control process.C. This indicates that the project manager is very aggressive and is likely to take the project to successful completion. Since he has announced the ‘no change requests’ policy, the customer manager can no longer request changes.D. This is unrealistic and impractical. The project manager should not have announced his intentions to the customer. He should have had an unofficial policy of rejecting all change requests. | Show Answer | B. This is unrealistic and impractical. Change is inevitable and rather than look at a ‘no change’ project, it would be more in the project interests to plan for a robust change control process. | Tagged with change control process project management | Tagged with change control process project management
PMP Question 22 | A project is contracted as a Cost-Plus-Fixed-Fee (CPFF) type of contract. The targeted cost is $200,000 with a fee of $30,000. If the project comes in at $170,000, what would be the cost of the total contract? | A. $195,500B. $230,000C. $200,000D. $170,000 | Show Answer | C. $200,000 | Tagged with contract Cost-Plus-Fixed-Fee (CPFF) | Tagged with contract Cost-Plus-Fixed-Fee (CPFF)
PMP Question 23 | As part of stakeholder analysis, a project manager drew up a power / interest grid. The project manager identified that a stakeholder could be classified low on the “interest” scale, and also as low on the “power” scale. What strategy should be used for such a stakeholder? | A. MonitorB. Manage closelyC. Keep informedD. Keep satisfied | Show Answer | A. Monitor | Tagged with stakeholder | Tagged with stakeholder
PMP Question 24 | David is managing a telecom network deployment project. The buyer of the telecom network is an external entity. Recently, the customer has requested all the future project updates to be automatically posted to their information system. In order to implement this, the project team needs to customize their project management information system so that it can be integrated with the customer’s information system. This is a new customer requirement that was not a part of the original project’s scope. What should the project manager do? | A. Request the customer to terminate the current contract and award a new contract.B. Ask the project team to customize the project management information system.C. Ignore the request as this is outside of the scope of the project.D. Initiate the formal change control process. | Show Answer | D. Initiate the formal change control process.
PMP Question 25 | Which of these is not a legitimate model used to analyze stakeholders? | A. Influence / impact gridB. Power / influence gridC. Sufficiency modelD. Salience model | Show Answer | C. Sufficiency model | Tagged with Influence / impact grid Power / influence grid Salience model Sufficiency model | Tagged with Influence / impact grid Power / influence grid Salience model Sufficiency model
PMP Question 26 | If you have an unresolved issue while working on a project, what is the best way to communicate that issue? | A. Assume that someone else is already working on itB. Write an email describing the issueC. Create an issue logD. Complain to a fellow colleague | Show Answer | C. Create an issue log
PMP Question 27 | The most recent analysis of Microcorp’s new fabrication facility renovation shows a CPI value of less than 1.0 What does this indicate? | A. The cost has overrun estimates.B. The cost has underrun estimates.C. The project is running ahead of schedule.D. The schedule has slipped. | Show Answer | A. The cost has overrun estimates. | Tagged with overrun estimates | Tagged with overrun estimates
PMP Question 28 | A software development project team has determined the best way to mitigate the risk of not having the computational resources to complete all bug testing on schedule is to add 3 more servers to the test bed. However, the network may not have enough capacity to handle the extra load of those three servers and could fail. This type of risk is called a ___________________ risk. | A. SecondaryB. SimulationC. BottleneckD. Hidden | Show Answer | A. Secondary | Tagged with Bottleneck Risk Hidden Risk Secondary Risk Simulation Risk | Tagged with Bottleneck Risk Hidden Risk Secondary Risk Simulation Risk
PMP Question 29 | Which of the following statements about products and projects is true? | A. Adding new functionality to an existing product cannot be considered as a project.B. A product life cycle is usually contained within a project life cycle.C. One product may have many projects associated with it.D. The product life cycle usually consists of non-sequential phases whereas the project life cycle consists of sequential phases. | Show Answer | C. One product may have many projects associated with it. | Tagged with non-sequential phases project life cycle | Tagged with non-sequential phases project life cycle
PMP Question 30 | The business case to justify a project typically contains: | A. BAC and ETC of the project.B. Cost Benefit AnalysisC. Project WBSD. Variance Analysis | Show Answer | B. Cost Benefit Analysis | Tagged with Cost Benefit Analysis Project WBS Variance analysis | Tagged with Cost Benefit Analysis Project WBS Variance analysis
PMP Question 31 | As part of the quality control in your project, you are looking at a technique which shows the history and pattern of variation. This is a line graph which shows data points plotted in the order in which they occurred. You are most likely looking at a: | A. Control chartB. Pareto diagramC. HistogramD. Cause and effect diagram | Show Answer | A. Control chart | Tagged with Cause and Effect diagram Control chart Histogram Pareto diagram | Tagged with Cause and Effect diagram Control chart Histogram Pareto diagram
PMP Question 32 | A hierarchical structure of resources organized by resource type category and resource type used in resource leveling schedules is known as: | A. Team structureB. Resource PoolC. Organization breakdown StructureD. Resource Breakdown Structure | Show Answer | D. Resource Breakdown Structure | Tagged with Organization breakdown Structure Resource Breakdown Structure Resource Pool Team structure | Tagged with Organization breakdown Structure Resource Breakdown Structure Resource Pool Team structure
PMP Question 33 | You are currently leading a project and performing the work defined in the project management plan. This activity relates to which of the following processes? | A. Direct and Manage Project WorkB. Validate ScopeC. Control ScopeD. Monitor and Control Project Work | Show Answer | A. Direct and Manage Project Work | Tagged with Control Scope | Tagged with Control Scope
PMP Question 34 | The accuracy of estimates of the cost of a project will _____________ over the life of a project. | A. be mitigatedB. remain neutralC. decreaseD. increase | Show Answer | D. increase
PMP Question 35 ( PMBOK 6th edition ) | Peter is a project manager who is assigned to a foreign country to manage a project. The project is a large one and comprises of smaller sub-teams, contributing to the entire project. As part of rewards and recognition within the project, Peter plans for a team award for the best sub-team. The Recognition and Rewards is associated with which of the following processes? | A. Close Project or PhaseB. Develop TeamC. Control QualityD. Manage Team | Show Answer | B. Develop Team | Tagged with Develop Project Team Manage Project Team Manage Team PMBOK 6th edition Recognition and Rewards | Tagged with Develop Project Team Manage Project Team Manage Team PMBOK 6th edition Recognition and Rewards
PMP Question 36 | Body language plays an important role in effective communications. This relates to which of the following communications dimensions? | A. NonverbalB. InformalC. VerbalD. Formal | Show Answer | A. Nonverbal | Tagged with effective communications Nonverbal | Tagged with effective communications Nonverbal
PMP Question 37 | A requesting organization for a project created a document that included the business need and the cost-benefit analysis. What would this document be termed as? | A. The project statement of workB. The business caseC. The project management planD. The contract | Show Answer | B. The business case | Tagged with business case contract project management plan | Tagged with business case contract project management plan
PMP Question 38 | You just found out that a major subcontractor for your project consistently provides deliverables late. The subcontractor approaches you and asks you to continue accepting late deliverables in exchange for a decrease in project costs. This offer is an example of: | A. ForcingB. SmoothingC. ConfrontingD. Compromise | Show Answer | D. Compromise | Tagged with Compromise Confronting Forcing Smoothing | Tagged with Compromise Confronting Forcing Smoothing
PMP Question 39 | A RACI chart is an example of a ___________ . | A. NetworkB. FlowchartC. Responsibility assignment matrixD. Hierarchical-type organization chart | Show Answer | C. Responsibility assignment matrix | Tagged with Flowchart RACI chart Responsibility assignment matrix | Tagged with Flowchart RACI chart Responsibility assignment matrix
PMP Question 40 | After receiving some news about a delay on one of your project tasks, you reviewed the schedule to determine how it will impact the project. While there is a substantial delay on this task, it is not a critical path item and will not impact delivery of any of your milestones. Another project manager advises you to only present the milestone chart during your meeting with the project stakeholders and tell them the project is progressing as planned. What do you do? | A. Present the project as a milestone chart and advise that the progress is tracking according to plan.B. Present the schedule in a milestone chart and disclose full details of the delay.C. Present the schedule in a network diagram and advise that the project is tracking according to plan.D. Present the schedule as a bar chart and advise that the project is tracking according to plan. | Show Answer | B. Present the schedule in a milestone chart and disclose full details of the delay. | Tagged with critical path milestone chart | Tagged with critical path milestone chart
PMP Question 41 | What term defines the work needed to complete a product, service, or result? | A. Product scopeB. Scope creepC. Scope verificationD. Project scope | Show Answer | D. Project scope | Tagged with Product scope Project scope Scope creep Scope verification | Tagged with Product scope Project scope Scope creep Scope verification
PMP Question 42 ( PMBOK 6th edition ) | A project manager is working on the Manage Quality phase of a project. He is looking for an iterative means to improve quality and eliminate activities that don’t add value. Which of the following will help him do this? | A. Quality control measurementsB. Quality checklistC. Continuous process improvementD. Team rewards | Show Answer | C. Continuous process improvement | Tagged with Continuous process improvement Manage Quality Perform Quality Assurance Quality checklist | Tagged with Continuous process improvement Manage Quality Perform Quality Assurance Quality checklist
PMP Question 43 | Why are the approved change requests input to the Direct and Manage Project Work process? | A. Approved change requests may be rejected by the project team during the Direct and Manage Project Work process.B. Approved change requests are implemented by the project team during the Direct and Manage Project Work process.C. Approved change requests are sent to the Change Control Board during the Direct and Manage Project Work process.D. Approved change requests are reviewed by the project team during the Direct and Manage Project Work process. | Show Answer | B. Approved change requests are implemented by the project team during the Direct and Manage Project Work process. | Tagged with Change Control Board change requests Manage Project Work | Tagged with Change Control Board change requests Manage Project Work
PMP Question 44 ( PMBOK 6th edition ) | You have successfully passed your PMP exam and are leading a project to replace the storage devices in a data center. In the following week, you and your team of experts will be meeting with a storage device vendor to discuss the status of their deliverables that are due at week’s end. What management process do these activities reflect? | A. Plan Procurement ManagementB. Control ProcurementsC. Conduct ProcurementsD. Control Resources | Show Answer | B. Control Procurements | Tagged with Close Procurements Conduct Procurements Control procurements Control Resources Procurements | Tagged with Close Procurements Conduct Procurements Control procurements Control Resources Procurements
PMP Question 45 ( PMBOK 6th edition ) | Which of the following is not an organizational process asset that is used during the Plan Resource Management process? | A. Template for organizational chartsB. Template for position descriptionsC. Standardized role descriptionsD. Standardized stakeholder list | Show Answer | D. Standardized stakeholder list | Tagged with Plan Human Resource Management process Standardized stakeholder list | Tagged with Plan Human Resource Management process Standardized stakeholder list
PMP Question 46 | Which of the following inaccurately describes a prototype? | A. A prototype is tangible and allows stakeholders to fine-tune their expectations.B. Requirements from a prototype are usually insufficient to move to the design phase.C. Prototypes support the concept of progressive elaboration.D. A prototype is a working model of the expected product. | Show Answer | B. Requirements from a prototype are usually insufficient to move to the design phase. | Tagged with prototype | Tagged with prototype
PMP Question 47 | Product scope is measured against the product requirements whereas project scope is measured against: | A. The WBS and WBS dictionaryB. The project scope statement and its associated WBS and WBS dictionaryC. The project requirements and WBS.D. The acceptance criteria | Show Answer | B. The project scope statement and its associated WBS and WBS dictionary | Tagged with acceptance criteria WBS dictionary | Tagged with acceptance criteria WBS dictionary
PMP Question 48 | A project charter that formally authorized a project was created. The project charter documented the initial requirements to satisfy stakeholders’ needs and expectations. How often should the project charter ideally be revised? | A. At the beginning, middle and end of a project.B. Once a monthC. NeverD. As required by the PMO. | Show Answer | C. Never | Tagged with project charter | Tagged with project charter
PMP Question 49 | A project manager prepared a presentation that included data on utilization of resources on her project, improvements in efficiency of the staff on the project, and the cost savings. She is doing this as part of what process? | A. Manage Stakeholder EngagementB. Monitor and Control Project WorkC. Control ScheduleD. Control Quality | Show Answer | B. Monitor and Control Project Work | Tagged with Manage Stakeholder Engagement Monitor and Control Project Work | Tagged with Manage Stakeholder Engagement Monitor and Control Project Work
PMP Question 50 | You are managing a project with over 130 procurement contracts. Because of the number of contracts, your project team includes a procurement manager and a procurement assistant. Company policy requires that certain types of procurements be advertised to potential bidders by means of newspaper advertisements. The procurement assistant typically reviews the bids received and short lists the suppliers for further review by the procurement team. During a meeting to review and select a vendor from the short listed suppliers, you discover that one of the suppliers is a company owned by your cousin. Which of the following is the best course of action? | A. Because the short list was prepared by the procurement assistant, not by you, you do not need disclose your relationship with the supplier, and may continue to participate in the selection process.B. Disclose your relationship with the provider and continue to participate in the selection process.C. Ask the procurement manager to lead the vendor selection process for this contract and excuse yourself from the review.D. Remove the supplier from the short list. | Show Answer | C. Ask the procurement manager to lead the vendor selection process for this contract and excuse yourself from the review. | Tagged with procurement | Tagged with procurement
PMP Question 51 | A company is looking for an experienced Project Manager to manage a large construction project. You meet all of the requirements for the position except for one. The organization is looking for a certified PMP with five years of experience and you have four years of experience managing similar projects. What is the BEST way to fill out your application? | A. Show how you meet the requirements but include your actual years of experienceB. Do not fill out that particular section.C. Explain why years of experience should not matter.D. Since you have plenty of experience, embellish your actual years of experience. | Show Answer | A. Show how you meet the requirements but include your actual years of experience | Tagged with PMI Code of Ethics Professional Conduct | Tagged with PMI Code of Ethics Professional Conduct
PMP Question 52 | You are managing an electronic chip design project for a customer. There are a number of engineers and subject matter experts from the customer’s organization that have been assigned as resources to the project, as well as several additional design engineers that have been supplied by your company. All the engineers have been involved in the development of a prototype chip; a very time consuming and expensive process. Upon the completion of the prototype, you submit it for review to ensure that there are no patent infringement issues with the design. When the results come back, it is determined that there are multiple issues that could result in an intellectual property dispute with the patent owners, should the prototype design be released commercially. The affected prototype elements were developed by resources from your company as well as your customer’s organization. What should you do? | A. Submit the prototype as is, as the budget and schedule do not accommodate rework.B. Ask the engineers to revise the design and resubmit it.C. Notify the project stakeholders immediately.D. Request permission to use the copyright material | Show Answer | D. Request permission to use the copyright material | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 53 | While sequencing activities for a project, the project management team applied certain discretionary dependencies. This was based on their knowledge of best practices within the project application area. What is the potential risk involved in using such dependencies? | A. They can create fixed float values and create external dependencies.B. They can create arbitrary float values and limit later scheduling options.C. They can create arbitrary float values and create external dependencies.D. They can create arbitrary float values and create mandatory dependencies | Show Answer | B. They can create arbitrary float values and limit later scheduling options. | Tagged with external dependencies fixed float mandatory dependencies | Tagged with external dependencies fixed float mandatory dependencies
PMP Question 54 | You are in the final phase of a low cost car manufacturing project. This project, as designed, has delivered a low cost car that runs on the battery. However, to close this project, many administrative standards are required to be followed in order to avoid auditing from Government authorities. Since your organization possesses experts who have tremendous knowledge in closing procedures and standards, you would like to use them to close this project. This effort is an instance of: | A. Using enterprise environmental factors in closing the projectB. Using expert judgment in closing the projectC. Using organizational process assets in closing the projectD. Poor project management practice | Show Answer | B. Using expert judgment in closing the project | Tagged with Expert judgment Poor project management practice | Tagged with Expert judgment Poor project management practice
PMP Question 55 | 20% of the work was completed in a project. At this stage the project manager determined that the budget at completion (BAC) was no longer viable and developed a forecasted estimate at completion (EAC). What index can the project manager use to look at the calculated projection of cost performance that must be achieved on the remaining work? | A. Schedule Performance Index (SPI)B. Cost Performance Index (CPI)C. Cost Variance (CV)D. To-Complete Performance Index (TCPI) | Show Answer | D. To-Complete Performance Index (TCPI) | Tagged with Cost Performance Index (CPI) Cost Variance (CV) Estimate at Completion (EAC) Schedule Performance Index (SPI) To-Complete Performance Index (TCPI) | Tagged with Cost Performance Index (CPI) Cost Variance (CV) Estimate at Completion (EAC) Schedule Performance Index (SPI) To-Complete Performance Index (TCPI)
PMP Question 56 | Some tools or techniques can be used across different project processes to plan, execute or control the characteristics of project elements. Which of the following is used as a tool in both Control Quality and Plan Quality Management processes? | A. BenchmarkingB. Statistical samplingC. Cost of qualityD. Design of experiments | Show Answer | B. Statistical sampling | Tagged with Benchmarking Design of experiments Statistical Sampling | Tagged with Benchmarking Design of experiments Statistical Sampling
PMP Question 57 | You are at work related social event and a colleague tells you another project manager has just hired her niece’s engineering firm for a city public improvement project that you are managing. You know that this company’s proposal did not meet the pre-defined selection criteria to be considered for award. What do you do? | A. File a complaint with PMI.B. Escalate the issue to the appropriate management.C. Ask the project manager about what you have just heard. If your suspicions are confirmed, escalate the issue to the appropriate management.D. Do nothing. | Show Answer | C. Ask the project manager about what you have just heard. If your suspicions are confirmed, escalate the issue to the appropriate management. | Tagged with PMI Code of Ethics | Tagged with PMI Code of Ethics
PMP Question 58 | The Control Procurements process ensures that the seller’s performance meets contractual requirements and that the buyer performs according to the terms of the contract. This process is part of which process group? | A. ExecutingB. ClosureC. PlanningD. Monitoring & Controlling | Show Answer | D. Monitoring & Controlling | Tagged with Control procurements | Tagged with Control procurements
PMP Question 59 | You are managing a project for your company constructing an office complex in another country. The construction work on 2 of the buildings is complete and is ready for move-in. However, the construction foreman informs you that a fee must be paid to a local government agency in order to be issued an occupancy permit for all new construction in that country. What should you do? | A. Pay the fee.B. Ask your legal department if this is legal.C. Notify project stakeholders that you have been asked to pay a bribe.D. Do not pay the fee. | Show Answer | A. Pay the fee. | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 60 | You have identified a risk that will negatively affect your security project. You and your team have decided to use an older encryption technology because of the high risk associated with the new technology. What type of risk strategy are you using? | A. MitigationB. ExploitationC. AvoidanceD. Transfer | Show Answer | C. Avoidance | Tagged with Avoidance Exploitation Mitigation | Tagged with Avoidance Exploitation Mitigation
PMP Question 61 | You have just joined a new organization as a project manager. You have heard a number of rumors about the procurement manager having possible underhanded dealings with suppliers. However, you have not been given any proof that these rumors are true. Your project requires a large number of dump trucks. Company policy mandates that all purchases go through the procurement department, rather than being handled by departmental employees. The value of the dump truck purchase is USD $395,000 and the contract was awarded to a supplier regularly used by your company. Shortly after taking delivery of the dump trucks, you learn that the procurement manager is driving a new car. What should you do? | A. Ask the procurement manager about the purchase of her new carB. Report this to the appropriate management.C. Talk to the supplier to find out if there was a bribe involved in the projectD. Do nothing. | Show Answer | D. Do nothing. | Tagged with PMI Code of Ethics and Professional Conduct supplier | Tagged with PMI Code of Ethics and Professional Conduct supplier
PMP Question 62 | You have met with your project sponsor and have been told that the project MUST be completed by the end of the year, no exceptions. This should be included in the project scope statement as a: | A. Project ConstraintB. Project BoundaryC. Project Acceptance CriteriaD. Project Assumption | Show Answer | A. Project Constraint | Tagged with Project Acceptance Criteria Project Assumption Project Boundary Project Constraint | Tagged with Project Acceptance Criteria Project Assumption Project Boundary Project Constraint
PMP Question 63 | A project manager drew up a resource histogram. On plotting the histogram, he found that some bars extended beyond the maximum available hours. What does this usually signify? | A. This means that the resources on those bars are being underutilized.B. This means that a resource optimization strategy needs to be appliedC. This means that the resources are producing outputs at a rate faster than the average rate.D. This means that resources need to be reduced from the project. | Show Answer | B. This means that a resource optimization strategy needs to be applied | Tagged with optimization strategy resource histogram | Tagged with optimization strategy resource histogram
PMP Question 64 | You applied for a project coordinator position in your organization. You have recently met with your director to learn more about the job functions of that position. Your director indicates that it is the functional managers who control the resources and not you in your new position. Which of the following represents the organization structure that you will be working in if you are chosen as a project coordinator? | A. ProjectizedB. Weak matrixC. Balanced matrixD. Strong matrix | Show Answer | B. Weak matrix | Tagged with Balanced matrix Projectized Strong matrix Weak matrix | Tagged with Balanced matrix Projectized Strong matrix Weak matrix
PMP Question 65 | Which of the following is a control tool that helps the project management team quantify and categorize defects according to sources? | A. Scatter chartB. Pareto diagramC. Control chartD. Cause and effect diagram | Show Answer | B. Pareto diagram | Tagged with Cause and Effect diagram Control chart Pareto diagram Scatter chart | Tagged with Cause and Effect diagram Control chart Pareto diagram Scatter chart
PMP Question 66 | Emily is producing a documentary on African wildlife. Although the project key stakeholders are very supportive of the project, Emily believes that there are some stakeholders’ concerns that might become major problems in the future. What should Emily do? | A. Treat them as project issues and address them immediately.B. Wait till these concerns become a problem.C. Request the stakeholders if they can resolve these concerns by themselves.D. Add these concerns to the risks watch list. | Show Answer | A. Treat them as project issues and address them immediately. | Tagged with project key stakeholders | Tagged with project key stakeholders
PMP Question 67 | Which of the following statements about team-building activities is incorrect? | A. It can be a 5-minute agenda item in a status review meeting.B. It can be a professionally facilitated experience designed to improve interpersonal relationships.C. The objective of team-building activities is to help team members work individually and effectively.D. Informal communication and activities help in building trust and establishing good working relationships. | Show Answer | C. The objective of team-building activities is to help team members work individually and effectively. | Tagged with communication | Tagged with communication
PMP Question 68 | A project manager analyzed the project’s communication requirements and decided that 10 out of the 30 stakeholders in the project would only need voicemail updates of certain information. This type of communication method is called: | A. Push communicationB. Pull communicationC. Interactive communicationD. On-demand communication | Show Answer | A. Push communication | Tagged with On-demand communication Pull communication Push communication | Tagged with On-demand communication Pull communication Push communication
PMP Question 69 | You are the project manager of a project executing work under a contract signed with a buyer organization. Just after the project has started, you notice that the buyer organization had made a mistake in the financial terms and your organization stands to benefit considerably through this oversight. What should your stance be? | A. Do not take any action since a contract is a binding and legal document.B. Discuss with your management on how you could gain a bonus due to the increased revenue your company stands to gain.C. Informally check with your counterpart in the buyer organization to see if they have noticed this error.D. Bring the error to the notice of the buyer organization and have an amendment made to the contract since this was in good faith. | Show Answer | D. Bring the error to the notice of the buyer organization and have an amendment made to the contract since this was in good faith. | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 70 ( PMBOK 6th edition ) | Which of the following processes goes beyond the distribution of relevant information and seeks to ensure that the information being communicated to project stakeholders has been appropriately generated, as well as received and understood? | A. Manage CommunicationsB. Control CommunicationsC. Manage Stakeholder EngagementD. Monitor Stakeholder Engagement | Show Answer | A. Manage Communications | Tagged with Control Stakeholder Engagement Manage Communications Monitor Stakeholder Engagement | Tagged with Control Stakeholder Engagement Manage Communications Monitor Stakeholder Engagement
PMP Question 71 | Jane is currently developing her project’s stakeholder register. She wants to identify the internal and external parties that are involved in the project. Which of the following documents can provide this information to Jane ? | A. Scope management planB. Project charterC. Stakeholder management planD. Project management plan | Show Answer | B. Project charter | Tagged with project charter Scope management plan Stakeholder management plan | Tagged with project charter Scope management plan Stakeholder management plan
PMP Question 72 | The Risk Management plan will usually contain the definitions of risk probability and impact. Which of the following has the highest impact (negative) on a project? | A. A rating of 1.1 on the impact scaleB. A rating of 0.8 on the impact scaleC. A rating of 0 on the impact scaleD. A rating of 0.1 on the impact scale | Show Answer | B. A rating of 0.8 on the impact scale | Tagged with impact scale Risk Management plan | Tagged with impact scale Risk Management plan
PMP Question 73 | Hillbrand Dairies is structured so project managers share responsibility with the functional managers for assigning priorities and directing the work of persons assigned to the project. This is an example of a organization. | A. Dotted lineB. HierarchicalC. TraditionalD. Matrix | Show Answer | D. Matrix | Tagged with Hierarchical | Tagged with Hierarchical
PMP Question 74 | Which of these is not a component of the scope baseline that is contained in the project management plan? | A. Work Breakdown Structure (WBS)B. Requirements documentationC. WBS DictionaryD. Project Scope Statement | Show Answer | B. Requirements documentation | Tagged with Project Scope Statement Requirements documentation Work Breakdown Structure (WBS) | Tagged with Project Scope Statement Requirements documentation Work Breakdown Structure (WBS)
PMP Question 75 | A project manager wants to proactively monitor a manufacturing process in order to determine if the quality level is within acceptable limits for that process. What tool will help with this? | A. Control chartsB. Ishikawa diagramC. HistogramD. PERT chart | Show Answer | A. Control charts | Tagged with Histogram Ishikawa diagram PERT chart | Tagged with Histogram Ishikawa diagram PERT chart
PMP Question 76 | As the Project Manager for Midway Carnival Rides, you are starting off on the Define Scope process. Which of the following is a key input to the process? | A. Risk Management PlanB. Quality Management PlanC. Project CharterD. Staffing Management Plan | Show Answer | C. Project Charter | Tagged with Quality Management Plan Staffing Management Plan | Tagged with Quality Management Plan Staffing Management Plan
PMP Question 77 | Your company is planning to bid on a project in an application area in which you have never worked before. You are aware that your company does not have any resources with the necessary expertise. Your management is pressurizing you to submit a bid. What should you do? | A. Refuse to do what your company management asks you to do since it violates the code of ethics and professionalism.B. Do what your management asks you to do. Your loyalty needs to be with your company. As long as management has the confidence that the project can be done, you can go with the plan.C. Do what your management asks you to do, but inform them that you would not like to be associated with the project since it violates the code of ethics and professionalism.D. Explain the gaps to your management clearly and also explain that this will be a stretch assignment. You can further explain to them that it is best to reveal to the potential buyer that your company does not possess the necessary skills, but are confident of ramping up the necessary skills and delivering the project successfully, based on your company’s track record. | Show Answer | D. Explain the gaps to your management clearly and also explain that this will be a stretch assignment. You can further explain to them that it is best to reveal to the potential buyer that your company does not possess the necessary skills, but are confident of ramping up the necessary skills and delivering the project successfully, based on your company’s track record. | Tagged with PMI Code of Ethics | Tagged with PMI Code of Ethics
PMP Question 78 | You are reviewing the response to an RFP issued by your company for a project that will last a year and exceed USD $5 million. Three vendors have been short listed. | You have many relationships with Xen Contractor staff that have been established during prior procurement contracts with this company. As a result a project manager from Xen Contractor with whom you are friendly both personally and professionally, calls you for clarification on a point mentioned in the 2nd section of the RFP. What should you do? |  | D. Send the clarification to all three vendors. | Tagged with PMI Code of Ethics and Professional Conduct RFP | Tagged with PMI Code of Ethics and Professional Conduct RFP
PMP Question 79 | You are in the middle of a risk assessment meeting with key stakeholders, customers and project team leaders. While identifying and assessing risks, you have realized that two key stakeholders are overemphasizing the impact of a risk. What is the BEST step you must take to avoid unfairness or bias when assessing risks? | A. Implement assumptions analysis to explore the validity of assumptionsB. Develop a risk response strategy to eliminate threatsC. Perform qualitative risk analysis to identify risk attitudesD. Perform sensitivity analysis to establish which risks have the most impact on the project | Show Answer | C. Perform qualitative risk analysis to identify risk attitudes | Tagged with qualitative risk analysis risk assessment | Tagged with qualitative risk analysis risk assessment
PMP Question 80 | Peter has been working for a retail company as a project manager. With his positive thinking and good managerial skills he turned many potentially disastrous projects into successes. Because of his expertise, the company high level executives offered him a group project manager position for a newly started environmental project. However, Peter learned that in his newly assigned project he may have to offer bribes to get the Government licenses. What should Peter do in such a situation? | A. Reject the offer because project managers should not engage in an unethical conductB. Accept the offer because project managers must obey their higher-upsC. Accept the position and offer bribes because project managers must complete projects on time and within budgetD. Investigate to find out if it is customary to offer bribes in that part of the country | Show Answer | A. Reject the offer because project managers should not engage in an unethical conduct | Tagged with PMI Code of Ethics and Professional Conduct | Tagged with PMI Code of Ethics and Professional Conduct
PMP Question 81 | Jane is estimating the overall expected cost of a new ERP system deployment project using the actual costs of an earlier similar ERP system deployment project as the basis for the cost. This is what type of estimating? | A. AnalogousB. Bottom-upC. Expert JudgmentD. Parametric | Show Answer | A. Analogous | Tagged with Analogous Bottom-up Expert judgment Parametric | Tagged with Analogous Bottom-up Expert judgment Parametric
PMP Question 82 | While analyzing a project, the project manager calculated the ratio of the Earned Value (EV) to the Actual Costs (AC) and obtained a value of 1.2. The project manager decided that this was an unfavorable condition to the project and decided to take corrective action. What is your view? | A. The project manager is correct. The ratio of EV to AC is called Cost Performance Index and a ratio greater than 1 is unfavorable to the projectB. The project manager is not correct. The ratio of EV to AC is called Cost Variance and a ratio greater than 1 is favorable to the project.C. The project manager is not correct. The ratio of EV to AC is called Cost Performance Index and a ratio greater than 1 is favorable to the projectD. The project manager is correct. The ratio of EV to AC is called Cost Variance and a ratio greater than 1 is unfavorable to the project | Show Answer | C. The project manager is not correct. The ratio of EV to AC is called Cost Performance Index and a ratio greater than 1 is favorable to the project | Tagged with Actual Costs (AC) Cost Performance Index Earned Value (EV) | Tagged with Actual Costs (AC) Cost Performance Index Earned Value (EV)
PMP Question 83 | Which of these is accurate regarding the Develop Schedule process? | A. Schedules are optimized such that all non-critical activities have a zero total float.B. The critical path method is a schedule network analysis technique that is performed using the schedule modelC. Schedule compression shortens the project schedule while changing the project scopeD. Schedule network analysis is a technique that is carried out once the schedule is approved. | Show Answer | B. The critical path method is a schedule network analysis technique that is performed using the schedule model | Tagged with Critical Path Method Develop Schedule process Schedule compression schedule network analysis | Tagged with Critical Path Method Develop Schedule process Schedule compression schedule network analysis
PMP Question 84 | What type of method can be used to eliminate personal bias during the process of selecting a seller? | A. Independent estimatesB. Source Selection CriteriaC. Vendor rankingsD. Screening | Show Answer | B. Source Selection Criteria | Tagged with Selection Criteria | Tagged with Selection Criteria
PMP Question 85 | During a project status review meeting, some of the project team members have raised a concern over the complexity of the project performance information reporting requirements. The project team is of the view that the work performance data should be sufficient for reporting. Which of the following is the best response that should be given to team members? | A. The work performance information is necessary for the conversion of the resisting project stakeholders to supportive project stakeholders.B. Compliance to the PMBOK requires transforming the work performance data to work performance information.C. This is a non-negotiable requirement and the project manager is not required to convince the team.D. The work performance data alone is not sufficient for effective decision making. | Show Answer | D. The work performance data alone is not sufficient for effective decision making. | Tagged with project stakeholders work performance | Tagged with project stakeholders work performance
PMP Question 86 | While managing a project, you decide to prepare an email for the project stakeholders describing the current project status. This is best described as an example of: | A. Vertical communicationB. Nonverbal communicationC. Informal communicationD. Formal communication | Show Answer | C. Informal communication
PMP Question 87 | You are working on an upgrade to a call distribution system for a call center, however you are finding it extremely difficult to get the proper resources assigned and tasks completed because the Call Center Manager is in control of the budget. You have just realized that you work in what type of an organization? | A. Balanced MatrixB. FunctionalC. Strong MatrixD. Projectized | Show Answer | B. Functional | Tagged with Projectized Organiszation Strong matrix | Tagged with Projectized Organiszation Strong matrix
PMP Question 88 | You are running one week behind on a project due to the late delivery by a vendor. You are forced to compress your project schedule due to a government mandated end date that constrains your project. After meeting with your team, the decision is to work several tasks in parallel that were scheduled to be run consecutively. This is an example of? | A. Risk AcceptanceB. CrashingC. Resource LevelingD. Fast Tracking | Show Answer | D. Fast Tracking | Tagged with Crashing Fast Tracking Resource Leveling Risk Acceptance | Tagged with Crashing Fast Tracking Resource Leveling Risk Acceptance
PMP Question 89 | How would you calculate your EAC if the ETC work will be performed at the budgeted rate? | A. EAC = BAC/CPIB. EAC= BAC-EVC. EAC = AC + BAC – EVD. EAC=(BAC-EV)*CPI | Show Answer | C. EAC = AC + BAC – EV
PMP Question 90 | One of the stakeholders of a project initiated a change request which was then documented in the change control system. In general, who would be responsible for approving or rejecting the change request? | A. An authority within the project management team or external organization.B. The sponsor.C. The stakeholder who raised the change request.D. The project manager. | Show Answer | A. An authority within the project management team or external organization. | Tagged with stakeholders | Tagged with stakeholders
PMP Question 91 | Which of the following is not an example of soft skills? | A. Emotional intelligenceB. Intelligence quotientC. Group facilitationD. Negotiation | Show Answer | B. Intelligence quotient | Tagged with Emotional intelligence Group facilitation Intelligence quotient Negotiation | Tagged with Emotional intelligence Group facilitation Intelligence quotient Negotiation
PMP Question 92 | John is the project manager of a global project. He finds that of late, there has been a deterioration in the quality of communication between various team members across the globe. What would you term this? | A. NoiseB. EncodingC. MediumD. Message | Show Answer | A. Noise | Tagged with Encoding Medium Message Noise | Tagged with Encoding Medium Message Noise
PMP Question 93 | You the project manager responsible for building a 100,000 sq. ft. data center. One of the schedule activities in your plan is to install the Computer Room Air Conditioning (CRAC) units, however in order to start the installation of the units the raised floor in the data center must be completely installed first, so the units have something to be bolted on to. This is an example of what type of dependency? | A. ExternalB. OptionalC. DiscretionaryD. Mandatory | Show Answer | D. Mandatory | Tagged with dependency | Tagged with dependency
PMP Question 94 | Failure Mode and Effect Analysis (FMEA) is a non-proprietary approach to Quality Management. This is an analytical procedure in which: | A. The effect of varying the various parameters that make up a process is determined by trying out various combinations of the parameters.B. Each potential failure mode in every component of a product is analyzed to determine its effect on the reliability of that component and, by itself or in combination with other possible failure modes, on the reliability of the product.C. A set of experts are asked to provide inputs on the reasons for failure of a product and corrective action is then taken.D. A list of historical causes for failure of a similar product is analyzed to determine the possible failure modes. | Show Answer | B. Each potential failure mode in every component of a product is analyzed to determine its effect on the reliability of that component and, by itself or in combination with other possible failure modes, on the reliability of the product. | Tagged with Failure Mode and Effect Analysis (FMEA) | Tagged with Failure Mode and Effect Analysis (FMEA)
PMP Question 95 | You are about to contract out a project to a service provider. However, at the time of awarding the contract, you are not sure of the total effort involved. Since the scope of work cannot be accurately estimated, you want to agree the per unit rates for difference services. Which of the following would best suit your purpose? | A. Cost-Plus-Fixed-Fee (CPFF)B. Time & Material (T&M)C. Fixed Price (FP)D. Cost-Plus-Incentive-Fee (CPIF) | Show Answer | B. Time & Material (T&M) | Tagged with Cost-Plus-Fixed-Fee (CPFF) Cost-Plus-Incentive-Fee (CPIF) Fixed Price (FP) Time & Material (T&M) | Tagged with Cost-Plus-Fixed-Fee (CPFF) Cost-Plus-Incentive-Fee (CPIF) Fixed Price (FP) Time & Material (T&M)
PMP Question 96 | While performing an audit on a project run by another project manager, a certified PMP, you find that project processes have not been followed, and that company procurement policies have been repeatedly violated. What do you do? | A. Develop a plan to deal with the associated problems.B. Ask the project manager to explain why these things have happened.C. Notify the appropriate management immediately.D. File a complaint with PMI | Show Answer | C. Notify the appropriate management immediately.
PMP Question 97 | As the project manager of a development project, you are aware that there is a slight defect in the product developed, as a result of which it will fail to meet certain regulatory standards. This was due to faulty requirements. You are also aware that the product will continue to function properly even though it fails to meet that standard. Your customer manager asks you to certify that the product meets the necessary regulatory standards, stating that this will not be verified when the report is submitted to the necessary authorities, so there is no issue with your certifying. Your stance is that: | A. You certify the product. Regulations are anyway guidelines in the industry. Not meeting a regulation does not mean anything.B. As a one-off instance, you will certify the product to make sure the project goes through successfully.C. You will not certify that a product meets certain regulations when it does not, even though the product continues to function well.D. You certify the product, but you document your conversation with your customer manager for future purposes. | Show Answer | C. You will not certify that a product meets certain regulations when it does not, even though the product continues to function well.
PMP Question 98 ( PMBOK 6th edition ) | A project manager has scheduled technical training for her project team members in order to increase their skills. During which of the following processes these training will be delivered to the team members? | A. Manage QualityB. Acquire ResourcesC. Develop TeamD. Plan Resource Management | Show Answer | C. Develop Team | Tagged with Acquire Project Team Develop Project Team Develop Team Manage Quality Perform Quality Assurance Plan Human Resource Management Plan Resource Management PMBOK 6th edition | Tagged with Acquire Project Team Develop Project Team Develop Team Manage Quality Perform Quality Assurance Plan Human Resource Management Plan Resource Management PMBOK 6th edition
PMP Question 99 | You are the sponsor of a project that is designed to record phone calls for quality control purposes. You are in the process of writing the charter, what is NOT an input into this document? | A. Organizational standard processesB. Marketplace conditionsC. Government or industry standardsD. Project Scope Statement | Show Answer | D. Project Scope Statement | Tagged with Scope Statement | Tagged with Scope Statement
PMP Question 100 | Which of the following processes gives the project management team insights into the health of the project? | A. Develop Project Management PlanB. Perform Integrated Change ControlC. Monitor and Control Project WorkD. Determine Budget | Show Answer | C. Monitor and Control Project Work | Tagged with Integrated Change Control | Tagged with Integrated Change Control