## General Reflections
Project 1: Class Curriculum | Project 2: CAPM Preparation
The first project that I took part in was Todd and I helping set up a structure for the class that would help everyone learn the technical details of Project Management. Since we both had some idea of Project Management principles, we tried our best to apply those principles as we did our project. While we were able to get the very initial deliverables involving a project, we did struggle in the middle and in the end when defining and controlling the project. I think one thing I learned aftewards was understanding the scope of the project. We only had one goal and a decent schedule that worked for the first half. However, as we went through the project, we realized that we didn't take into account any risks associated with the project, control, what resources we needed, and overall, had no quality management. We didn't have any documentation or evaluation methods to see if what we were doing was working. With my final project with Wen, I realized it didn't work because comments from several students said that it was good at first but they needed more application other than just learning. | The second project that I was involved in was a personal project. This personal project had a goal of helping me prepare to take the CAPM certification at the end of the course. Again, I had applied the principles of what I knew already to help plan, scope, budget, and prepare my project. It was pretty simple to plan out my resources, budget (it was fixed), and work towards my goal. However, the same problems appeared. The project was succeeding at the beginning then quickly it started to fall behind, there were risks not planned for and no responses, and again, there was no way of checking if this project was even succeeding. I was needing direction and help from Brother Godfrey with certain topics and more importantly, I was needing a way for me to apply all the information I was learning. I was simply learning book knowledge. It was interesting as well because in the end, I was not able to reach my goal. Poor time management and responses to risks like aid and application really hindered the progress of this goal. I realized I was not learning anything from my previous project.
Project 3: Python | Project 4: Course Evaluation
With this third project, I feel like I finally learned from the first two certain aspects of Project Management that we failed at. This time, there was a bigger team involved witht his project. We wanted to learn Python and create a program by the end of this project. At the beginning, we defined the goal, got the resources that we needed, built the team, and proceeded with the project. However, at the time, we didn't know why, the project was failing faster than the first two. We were focused on several aspects of the project that we had not done so well previous. For example, we outlined the plan, the risks, even made out assignments for each of us to do. However, I think because we focused on what we failed on before, we had forgotten all the simple things associated with PM that still required attention for it to be succesful. | The final project really show-cased the overall the learning and application of the previous projects and knowledge learned from project management. This project had a goal of creating a survey and interview questions to gather useful data for Brother Godfrey and for students in the future. The project has been extremely succesful because I think of the principles I have learned from the 3 previous projects. Each previous project had one aspect that was succesful and definitely one that failed. For example, one project, time management was well-controlled and planned out, however, quality management suffered. This happened through each project and fluxuated between different PM principles. However, with this projected, we really executed and planned out deliverables with this project and had hard deadlines, understood risks associated with it, and really held ourselves accountable of completing this project. Along with that, I think because it was the end of the semester and we were focusing on the "quality" and evalution of the course, we focused on that with this project and made sure what we were doing was going to be useful AND it was meeting the goals. Three modes were also present thorughout each phase of this project
`

## QA - Three Modes
Am I Growing as Project Manager (Dependent, Independent, Interdependent)?
Dependent | What I Learned | Independent | What I Learned | Interdependence | What I Learned
Project Charter: Inputs | For developing charters, I really could not deliver a a completed charter without having to meet with "stakeholders" and my team specifically. I was also dependent of what I already knew/didn't know about the project. | Time Management | Even though items and deliverables with the projects I had were planned together with a group, time management was an independent task that I needed to control. From a PM point of view, I learned it was also on them to help the project stay on time. | Application of PM Principles | Learning more about the application of PM principles was mostly an independent task, and I thought that I would be able to apply it myself as well, but I realized I really needed help with apply it in real-life situations.
Project Phases | I did well and did not do well with this. With my independent projects, I excelled pretty well with this principle of dividng the projects into measurable/deliverable sections. Again, with the Python team, we only had the goal of the project and nothing else. | Project, Program, Portfolio Management | I was already familiar with these principels, so most of what I learned about PPP Management was independent. I studied the PMBOK and was actually able to present it during class one time. | Scope Management | Scope was an interesting topic that I actually needed help figuring out with the projects because I usually had my own idea about the scope of each project I was working on. But after speaking and learning more about it, I realized I have to really understand what I'm accomplishing.
Develop Schedule | For my personal projects, I was able to complete this by myself, but with my other projects, I really was dependent on the team's schedule as a whole. However, with this final project I'm doing with Wen, I’m realizing the importance of setting deadlines and committing to them. | Project Charter | While getting the informaiton and resources was what I considered to be dependent mode, developing the actual charter was something mostly independent. Prior to this class, I was always very dependent on someone else creating it. | Project Planning | At the beginning of the semester, I definitely though project planning was more independent to the PM. I quickly learned through application that I really needed help from Stakeholders and the team members in all parts of project planning.
Resources | Again, the succes of the projects I worked on solely depended on the resources that were available to me. Looking at it differently, the resources I was going to use was dependent on my own research and use. | Cost Management | I did not really have a chance to apply this in a very extensive manner. My only project that required costs was my independent learning course. The CAPM costs $300 and that was a fixed budget. There were optional courses involved but they were out of scope. | Defining Activities | Especially with the team project, this was really important for me to be more interdependent because each team member has their own responsbilities and their own activities that I can't really define for them. It had to be a team effort.
Developing Team | My first two projects were more independent since it was developing a learning course for myself. However, we started a Python project that actually failed and I learned a lot about the different skills needed to have a successful team and how different individual goals makes it difficult. | Estimating Costs | Again, I did not really have an opportunity to apply this. I did the Harvard PM PM simulator that helped me "estimate" costs for the project, but it's all formulated so it was not a very good measure of application. | Managing Quality | Sometimes I still think this has qualities of me being in the independent mode, but gather input from team members and input from outside sources really helped with managing quality. I met with Brother Godfrey several times about this principle and still need help with it.
Risk Responses | We started creating a risk register for the Python project and we got about half way done with it. However, because of several factors, we realized our mitigation/reponses were not very well thought it and consequently, the project failed. But we learned how it important it is to plan for that. | Risk Management | Like previously mentioned, risk management was not well handled in the Python group project because of the lack of planning and creating the risk register. The reponses we created were also very minimal and were not going to help. As a result, I decided to re-study this part of PM. | Communications | Communication is definitely a principle of PM that I learned has to be completely interdependent for a project to be a successful and for a PM to be succesful. Also, you can't really communciate without being interndepend with the team/stakeholders.
|  | Managing Team | I feel like this principle of managing a team (resources, budget, timelines, emotions, etc.) was something that I had to learn independently and help myself improve. With the team project, I feel like that is where my weaknesses where shown and learned from it.

## QA - 5 Outcomes
Am I Growing as Project Manager (Dependent, Independent, Interdependent)?
Project 1 | Class Curriculum | Outcome | Outcome Hours | Hours
Preparation | Significant | 1, 2, 4 | 9 | 30
Teaching | Outstanding | 1, 2, 3 | 12
PM Application | Significant | 2, 3, 5 | 9
Project 2 | PM Certification | Outcome | Outcome Hours | Hours
Preparation | Outstanding | 1, 2, 4 | 12 | 27
Teaching | Significant | 3, 5 | 6
PM Application | Significant | 3, 4, 5 | 9
Project 3 | Python Learning | Outcome | Outcome Hours | Hours
Preparation | Beginning | 1, 2 | 2 | 12
Teaching | Sufficient | 1, 2, 4 | 6
PM Application | Sufficient | 3, 5 | 4
Project 4 | Python Learning | Outcome | Outcome Hours | Hours
Preparation | Significant | 1, 2 | 6 | 27
Teaching | Significant | 1, 4, 5 | 9
PM Application | Outstanding | 3, 4, 5 | 12
Grow in the capacity and disposition to act and not be acted upon.
Develop additional comprehension and capacity for stewardship and consecration.
Develop and execute project plans according to modern project delivery methodologies while working within real life constraints.
Expand and deepen knowledge of, awareness of, and experience with how to lead and work individually, within a team, and within an organization to accomplish operational, tactical, and strategic level objectives, outcomes, and initiatives.
Create, practice, and implement professional oral and written presentations, reports, consumable solutions, and project-oriented deliverables.

## QA - Time Tracking
Am I Growing as Project Manager (Dependent, Independent, Interdependent)?
| Cumulative Grade |  | Current Grade | Project 1 | Course Evaluation | Project 2 | PM Certification
| Hours | Grade | 155 | Work | 5 | Work | 27
| 0 | F | A | Outcome Hours | 30 | Outcome Hours | 27
| 40 | D-
| 50 | D |  | Project 3 | Python Learning | Project 4 | Evaluations
| 60 | D+ |  | Work | 12 | Work | 15
| 70 | C- |  | Outcome Hours | 12 | Outcome Hours | 27
| 80 | C
| 90 | C+
| 100 | B-
| 110 | B
| 120 | B+
| 130 | A-
| 140 | A

## PM Certification
Project Status
| Project | Preparing for CAPM
| Project Manager | Napoleon Galang
| Updated On | 2019-10-23
| Planned Start Date: | 2019-10-07 | Uncompleted: | 2
| Planned Finish Date: | 2019-12-13 | Schedule: | Behind
|  |  | Est. Budget: | 300
Tasks Overview
| Name | Planned Finish Date | Planned Hours | Actual Hours | Percent Complete | Status | Comments
Section 1 | Chapter 1 | 2019-10-09 | 1 | 1 | 100% | Completed
| Chapter 2 | 2019-10-09 | 1 | 1 | 100% | Completed
| Chapter 3 | 2019-10-09 | 1 | 1.75 | 100% | Completed
| Chapter 4 | 2019-10-24 | 0.75 | 1.25 | 100% | Completed
| Chapter 5 | 2019-10-24 | 1 | 1.75 | 100% | Completed | Discussed WBS with Brother Godfrey.
| Chapter 6 | 2019-10-26 | 0.75 | 1.25 | 100% | Completed | Skimmed over it. Need to go in more detail.
| Chapter 7 | 2019-10-27 | 1 | 1.5 | 100% | Completed
| Chapter 8 | 2019-10-28 | 0.75 | 1.75 | 100% | Completed
| Chapter 9 | 2019-10-29 | 1 | 1.75 | 100% | Completed
| Chapter 10 | 2019-11-01 | 1 | 2 | 100% | Completed
| Chapter 11 | 2019-11-03 | 1 | 2 | 100% | Completed
Section 2 | Chapter 2.1 | 2019-11-06 | 1.5 | 1 | 100% | Completed
| Chapter 2.2 | 2019-11-09 | 1.5 | 1 | 100% | Completed
| Chapter 2.3 | 2019-11-11 | 2 | 1 | 100% | Completed
| Chapter 2.4 | 2019-11-14 | 2 | 1 | 100% | Completed
| Chapter 2.5 | 2019-11-17 | 1 | 0 | 0% | Not Started
| Chapter 2.6 | 2019-11-20 | 1 | 0 | 0% | Not Started
0%

## PM Data
Decisions History
Wk. | Target Scope | Target Cmpltn. | Team Size | Team Skill Level | Outsourcing | Protos. | Meetings | Overtime | Chapter 1 | 86.44%
17 | Wireless | 1800% | 600% | High | Extensive | 4 | Coaching: 1 Standup: 1 Status: 2 | Allowed | Chapter 2/3 | 100%
16 | Wireless | 1800% | 400% | Medium | Extensive | 4 | Coaching: 1 Standup: 1 Status: 2 | Allowed
15 | Wireless | 1800% | 500% | Medium | Primary Tasks | 4 | Coaching: 1 Standup: 1 Status: 3 | Allowed
14 | Wireless | 1800% | 500% | Medium | Primary Tasks | 4 | Coaching: 1 Standup: 3 Status: 3 | Allowed
13 | Wireless | 1800% | 500% | Medium | Primary Tasks | 5 | Coaching: 0 Standup: 1 Status: 3 | None
12 | Wireless | 1800% | 500% | Medium | Primary Tasks | 5 | Coaching: 1 Standup: 1 Status: 4 | None
11 | Wireless | 1800% | 200% | High | Primary Tasks | 5 | Coaching: 1 Standup: 1 Status: 4 | None
10 | Wireless | 1800% | 400% | Medium | Primary Tasks | 5 | Coaching: 1 Standup: 2 Status: 4 | None
9 | Wireless | 1800% | 400% | Medium | Primary Tasks | 5 | Coaching: 1 Standup: 2 Status: 4 | None
8 | Wireless | 1800% | 500% | Medium | Support Tasks | 5 | Coaching: 0 Standup: 0 Status: 4 | None
7 | Wireless | 1800% | 500% | Medium | Support Tasks | 5 | Coaching: 0 Standup: 1 Status: 4 | Allowed

## Evaluation Data
Beginning | 1
Sufficient | 2
Significant | 3
Outstanding | 4