## 23
Risk = Impact * Likelihood
Corrective
WBS Element | BCE | BTE (Weeks) | Cost | Time | Likelihood | Risk Time (RT) | Risk Cost (RC)
L | 20000 | 9 | 4000 | 2 | 0.2
V | 16000 | 8 | 4000 | 2 | 0.3
T | 32000 | 5 | 8000 | 2 | 0.1
U | 20000 | 7 | 12000 | 3 | 0.2
S | 16000 | 3 | 4000 | 1 | 0.3
J | 18000 | 3 | 4000 | 1 | 0.1
R | 10000 | 4 | 4000 | 3 | 0.3
C | 15000 | 6 | 5000 | 2 | 0.3
a. Determine the risk time (RT) and risk cost (RC) for all the WBS elements of the project
(Enter in cells G4:H11 above)
b. Consider the risk times on non-critical paths. Which activities and paths should be watched carefully as posing the highest risks to the project duration?
c. What are the expected time (ET) of the critical path, and the expected costs (EC) of the project?
ET
EC
L
9
C
6
J
3
R
4
V
8
End
U
7
T
5
S
3

## 24
Corrective
WBS Element | BCE | BTE (Weeks) | Cost | Time | Likelihood | RT | RC
L | 20000 | 9 | 4000 | 2 | 0.2 | 0.4 | 800
V | 16000 | 8 | 4000 | 2 | 0.3 | 0.6 | 1200
T | 32000 | 5 | 8000 | 2 | 0.1 | 0.2 | 800
U | 20000 | 7 | 12000 | 3 | 0.2 | 0.6 | 2400
S | 16000 | 3 | 4000 | 1 | 0.3 | 0.3 | 1200
J | 18000 | 3 | 4000 | 1 | 0.1 | 0.1 | 400
R | 10000 | 4 | 4000 | 3 | 0.3 | 0.9 | 1200
C | 15000 | 6 | 5000 | 2 | 0.3 | 0.6 | 1500
|  |  | 20000 | 10 | 0.3 | 3 | 6000
Because of its geographical location, the Largesse hydro project is threatened with weather-associated delays and costs. The likelihood of bad weather is estimated at 0.30 with a potential impact of delaying work by 10 weeks and increasing the cost by $20,000
a. Ignoring the time an cost risks in Problem 23, what are the expected project completion time and completion cost of the weather risk alone?
ET
EC
b. What are the estimated expected project completion time (ET) and cost (EC) considering the weather risk and the risks listed in Problem 23?
ET
EC
Note: I still am using the critical path that does not include J and U because I am considering them to be near critical for the purpose of calculations.
L
9
C
6
J
3
R
4
V
8
End
U
7
T
5
S
3

## 25
Softside Systems has a $100,000 fixed price contract for installation of a new application system. The project is expected to take 5 weeks and cost $50,000. Experience with similar projects suggests a 0.30 likelihood that the project will encounter problems that could delay it by as much as 3 weeks and increase the cost by $30,000. By increasing the project staff by 20 percent for an additional cost of $10,000, the likelihood of problems would be reduced to 0.10, and the delay and cost to 1 week and $8,000, respectively. Set up a decision tree to show whether Softside should increase the size of the project staff.
Decision Trees are probably easier to draw by hand, however use the symbols below to build a decision tree in the spreadsheet if you choose.
| Decision Node | Fixed Price |  | Legend | Profit | Time | Costs
|  | 100000 |  | EMV
EC/ET
Uncertainty Node
Connector
No increase
Increase staff

## 26
Corecast Contractors has been requested by a municipality to submit a proposal bid for a parking garage contract. In the past, the cost of preparing bids has been about 2 percent of the cost of the job. Corecast project manager Bradford Pitts is considering three possible bids: cost plus 10 percent, cost plus 20 percent, and cost plus 30 percent. Of course increasing the "plus percent" increases the project price and decreases the likelihood of winning the job. Bradford estimates the likelihood of winning the job as shown in the table below:
Decision Trees are probably easier to draw by hand, however use the symbols below to build a decision tree in the spreadsheet if you choose.
| Decision Node |  | Bid Price | P(Win) | P(Lose) |  | Legend
|  | P1 | C+0.1C=1.1C | 0.6 | 0.4 |  | EMV
|  | P2 | C+0.2C=1.2C | 0.4 | 0.6 | Profit | EC
| Uncertainty Node | P3 | C+0.3C=1.3C | 0.2 | 0.8
Connector

## 27
Iron Butterfly Company submits proposals in response to RFPs and faces three possible outcomes: N1, Iron Butterfly gets a full contract; N2, it gets a partial contract (job is shared with other contractors); N3, it gets no contract. The company is currently assessing three RFPs, coded P1, P2, and P3. For P3, the customer will pay a fixed amount for proposal preparation; for P1 and P2, Iron Butterfly must absorb the proposal preparation costs, which are expected to be high. Based upon project revenues and proposal preparation costs, the expected profits ($ thousands) are as shown in the table below:
To which RFPs would Iron Butterfly respond using the three decision criteria (e.g. maximax - risk seeking, maximin - risk averse, minimax - minimize regret)?
Proposals | N1 | N2 | N3
P1 | 500 | 200 | -300
P2 | 300 | 100 | -100
P3 | 100 | 50 | 25
Maximax
Maximin
Minimax
Which would you choose and why?
| regret table |  |  | max op loss | Maximax | Maximin
p1
p2
p3

## 28
Frank Wesley, project manager for the LOGON project, is concerned about the development time for the robotic transporter. Although the subcontractor, Creative Robotics (external dependency), has promised a delivery time of 6 weeks, Frank knows that the actual delivery time will be a function of the number of other projects Creative Robotics is working on. As an incentive to speed up delivery of the transporter, Frank has three options:
S1: Do nothing S2: Promise Creative Robotics a future contrct with Iron Butterfly S3: Threaten to never contract with Creative Robotics again if they are late.
He estimates the impact of these actions on delivery time would be as follows in the table below:
Payoffs: | Creative Robotics Workload
Strategy | Slow | Average | Busy
S1 | 4 | 6 | 8
S2 | 3 | 4 | 7
S3 | 3 | 6 | 6
What strategy should Frank adopt based upon uncertainty criteria (maximax = risk seeking, maximin = risk averse, minimax = minimize regret, EV = Expected value or maximum expected payoff? Please note that the criteria must be adapted here because the goal is to minimize the payoff (time) rather than the typical maximizing of payoff goals.
Maximax
Maximin
Minimax
Expected Value (EV)
Which would you choose and why?
| Maximax | Maximin |  | Regret table | Max op loss | expected value
S1
S2
S3